## Architectural Bugs
ID | Title | Status | Category | Severity | Priority | Description | Recommended_Solution | Evidence | Review_Phase | Effort | Owner | Dependencies | Decision
CEO-001 | No verified authentication or authorization boundary | Open | Security | Critical | P0 | The orchestration API and connector routes expose enterprise extraction and product data operations without visible user identity, role checks, or source-level entitlements. | Make enterprise SSO and server-side authorization a production gate. Define roles, source entitlements, product-level access checks, and denied-access audit events before wider rollout. | Orchestration.API/Program.cs; frontend/app/api/bom-*.ts; no auth middleware or endpoint attributes found. | Production gate | XL | TBD |  | Required
CEO-002 | Development CORS policy is unrestricted | Open | Security | Critical | P0 | The API uses AllowAnyOrigin, AllowAnyMethod and AllowAnyHeader. In a reachable environment this weakens the browser trust boundary. | Replace with environment-specific allowlists, explicit methods and headers, credential policy, and automated configuration tests. Fail startup if production uses the development policy. | OrchestrationPlatform/Orchestration.API/Program.cs: AllowAnyOrigin/Method/Header. | Production gate | S | TBD |  | Required
CEO-003 | Configit credential handling is unsafe by design | Open | Security | Critical | P0 | Repository documentation says the Configit base URL, API key and SSL verification setting are embedded in config.py. This creates secret exposure and rotation risk. | Remove embedded credentials, rotate any exposed key, use a secret vault or protected environment injection, and scan Git history. Never expose debug raw responses to untrusted callers. | configit_extractor/README.md; references to embedded API key and config.py. | Production gate | M | TBD |  | Required
CEO-004 | Connector subprocesses execute inside web request paths | Open | Architecture | High | P0 | Next.js API routes locate Python and run extractors directly. Long-running connector work is coupled to web process lifetime, filesystem layout, and request timeout. | Move connector execution behind the orchestration service and durable job queue. Keep Next.js as BFF/UI only. Use versioned job APIs and event streaming. | frontend/app/api/bom-configit/route.ts; frontend/app/api/bom-windchill/route.ts. | Architecture foundation | L | TBD |  | Required
CEO-005 | Jobs are in-memory and disappear on restart | Open | Reliability | Critical | P0 | Job state is held by an in-memory JobStore. Restarting the API can orphan running work and erase diagnostic state. | Persist job metadata and terminal outcomes in SQL; store payloads in a versioned snapshot/object store. Rehydrate active jobs after restart and mark unknown workers explicitly. | Orchestration.API/Services/JobStore.cs; Program.cs service registration. | Architecture foundation | L | TBD |  | Required
CEO-006 | Runtime output is written inside the repository | Open | Operations | High | P0 | SAP job directories and extractor outputs accumulate under source folders, mixing runtime data, product IP and code. | Move runtime data to configured application-data/object-storage locations outside the repo. Add retention, cleanup, access controls, encryption and startup validation. | SAP-BOM-Extractor/runtime/jobs; untracked job_* folders in audit. | Stabilization | M | TBD |  | Required
CEO-007 | Runtime outputs and test fixtures are not clearly separated | Open | Data governance | High | P0 | Extraction JSON files are repeatedly modified or deleted while also serving as samples or current output. This makes demos, tests and operations ambiguous. | Create immutable sanitized fixtures under fixtures/contracts and fixtures/edge-cases. Ignore runtime/latest outputs and identify every committed data file by purpose and classification. | tc_extraction.json deletions; windchill_extraction.json, configit_extraction.json and sap_bom_extraction.json history. | Stabilization | M | TBD |  | Required
CEO-008 | Teamcenter polling can continue for about 50 minutes | Open | Reliability | High | P0 | Legacy BOM streaming allows 2,000 attempts at 1.5 seconds each. This masks stuck jobs, creates network load and gives users no bounded terminal outcome. | Replace with durable job status plus SSE reconnection, maximum wall-clock deadline, cancellation and explicit TIMED_OUT/WORKER_LOST states. | frontend/components/BomStreamViewer.tsx: TEAMCENTER_MAX_FETCH_ATTEMPTS=2000 and 1500 ms delay. | Stabilization | M | TBD |  | Required
CEO-009 | SourceBomPanel is a platform-level responsibility hotspot | Open | Architecture | High | P0 | One component owns fetching, polling, transformation lifecycle, tree, 2D, 3D, fullscreen, comparison, impact, requirements and global overlays. It is the most frequently touched meaningful file. | Keep the visual shell but separate SourceRuntimeController, BomWorkspaceState, VisualizationHost and page-level GlobalOverlayHost. Decompose by ownership, not by arbitrary file size. | frontend/components/SourceBomPanel.tsx; 12 touches in 30-day audit. | Architecture foundation | L | TBD |  | Required
CEO-010 | Workspace page is a growing source-specific state machine | Open | Architecture | High | P0 | The comparison page holds independent state branches and request flows for Teamcenter, SAP, Configit, Windchill, Excel, revisions, change impact and comparison. | Introduce a typed source-adapter registry and reducer/state machine. Each adapter defines form, start/load behavior, capabilities and cleanup while common workspace lifecycle remains centralized. | frontend/app/bom-comparison/page.tsx; 11 touches and many source-specific states/branches. | Architecture foundation | L | TBD |  | Required
CEO-011 | BOM transformation logic is duplicated | Open | Maintainability | High | P0 | Teamcenter, Configit and related transforms exist in multiple viewers and page-level code, with differing payload assumptions and identity behavior. | Create one pure adapter per source with schema validation, canonical mapping and versioned fixtures. Delete or archive obsolete viewers only after usage verification. | BomViewer.tsx; BomStreamViewer.tsx; page.tsx SAP transform; source adapter logic. | Architecture foundation | M | TBD |  | Required
CEO-012 | Canonical BOM model is too weak for enterprise comparison | Open | Data architecture | Critical | P0 | TreeNodeData mixes identity and attributes in free-form maps. It does not reliably distinguish part master, occurrence, relationship, source revision, effectivity, units or provenance. | Define CanonicalBomSnapshot, PartIdentity, OccurrenceIdentity and BomRelationship contracts. Preserve raw source payload reference and transformation version. Provide compatibility projection to TreeNodeData during migration. | types/bom-comparison.ts; transforms use Record<string, scalar> attributes. | Architecture foundation | XL | TBD |  | Required
CEO-013 | Cross-system identity is heuristic but appears authoritative | Open | Product trust | Critical | P0 | Comparison and impact rely on item IDs and normalized names. Users may interpret probable matches and corresponding parts as confirmed digital-thread links. | Create an identity confidence model with fact/rule/suggestion labels. Persist approved cross-references, show alternatives, and prevent heuristic matches from silently becoming authoritative. | lib/bom-comparison.ts; cross-bom-impact and requirement matching flows. | Core intelligence | L | TBD |  | Required
CEO-014 | Comparison uses greedy matching rather than global assignment | Open | Core intelligence | High | P1 | Pairwise candidate consumption can produce locally plausible but globally inferior cross-source matches, especially with repeated names and occurrences. | Benchmark deterministic bipartite/global assignment for ambiguous candidate groups. Retain exact IDs first, then solve constrained candidate sets and expose why a candidate won. | frontend/lib/bom-comparison.ts matching sequence and used-candidate behavior. | Core intelligence | L | TBD |  | Required
CEO-015 | Comparison thresholds are not calibrated by source pair | Open | Core intelligence | High | P1 | A fixed heuristic threshold is applied across PLM, CPQ, ERP and Excel despite different naming, hierarchy and revision semantics. | Build versioned benchmark fixtures per source pair, measure precision/recall, and configure policies by Teamcenter-SAP, Windchill-SAP, PLM-Configit, Excel-source, etc. | frontend/lib/bom-comparison.ts score threshold and weights. | Core intelligence | M | TBD |  | Required
CEO-016 | Quantity and unit semantics are not normalized | Open | Data quality | High | P0 | Sources represent quantity and unit in different formats. String comparison can create false differences or miss meaningful ones. | Use decimal quantity plus explicit UOM, source value, conversion status and precision. Compare only when units are compatible and explain skipped comparisons. | Source transforms; comparison type fields; Configit quantity rendered as string. | Architecture foundation | M | TBD |  | Required
CEO-017 | Revision, configuration and effectivity context are not first-class | Open | Data architecture | Critical | P0 | A BOM without revision rule, view, plant, date, variant selections and effectivity is not reproducibly comparable. | Require SnapshotContext on every extraction. Show it in workspace and exports; block or warn when comparing incompatible contexts. | Connector inputs and TreeNodeData omit consistent extraction context. | Architecture foundation | L | TBD |  | Required
CEO-018 | No durable BOM snapshot or reproducible session | Open | Product | High | P0 | Loaded roots and comparison sessions vanish on refresh, making results non-reproducible and preventing audit, sharing and later review. | Persist immutable snapshots and saved workspaces with extraction timestamp, connector version, context and user. Use URLs that reference saved sessions without exposing identifiers directly. | Frontend module/local state; no demonstrated snapshot persistence. | Platform productization | XL | TBD |  | Required
CEO-019 | Requirement traceability is demo data but can look live | Open | Product trust | Critical | P0 | Requirement history is loaded from local structured data while UI presents rich traceability semantics. Stakeholders may infer authoritative ALM connectivity. | Add a persistent DEMO DATA badge and provenance panel now. Later implement a permission-aware Codebeamer connector with explicit trace links and timestamps. | frontend/data/hardcoded-part-requirements.json; requirement trace store and drawer. | Stabilization | S | TBD |  | Required
CEO-020 | Global overlay ownership is implemented through a singleton workaround | Open | Architecture | High | P0 | RequirementsExplorerModal is instantiated by repeated source panels and suppresses duplicates using a module-level activeOwner symbol. | Mount one GlobalOverlayHost at workspace page level. Overlays subscribe to central workspace state and never depend on which source panel mounted first. | RequirementsExplorerModal.tsx activeOwner; RequirementTraceWorkspace.tsx intentionally empty; SourceBomPanel.tsx overlayOwner. | Architecture foundation | M | TBD |  | Required
CEO-021 | Multiple legacy BOM viewer implementations remain active in source | Open | Maintainability | Medium | P1 | BomViewer, BomStreamViewer and SourceBomPanel overlap. Legacy polling and transform code can be accidentally reused or misread as current truth. | Run import/reference analysis, designate SourceBomPanel architecture as current, migrate reusable pure transforms, then delete or archive dead viewers with a regression build. | frontend/components/BomViewer.tsx; BomStreamViewer.tsx; SourceBomPanel.tsx. | Stabilization | S | TBD |  | Required
CEO-022 | Dropped Radial Explorer remains in code and host logic | Open | Product coherence | Medium | P1 | The product direction dropped the standalone radial view, but component, layout types and SourceBomPanel branch remain. | Verify no user route depends on it, remove component/import/types/tests, and update documentation. Keep radial-clusters only as a Constellation layout term. | BomRadialExplorerView.tsx; SourceBomPanel.tsx radial branch; master documentation drift. | Stabilization | S | TBD |  | Required
CEO-023 | Product promise exceeds implemented connector reality | Open | Strategy | High | P0 | Homepage and source picker mention Codebeamer, Oracle and Servigistics even though active source definitions support Teamcenter, Windchill, SAP, Configit and Excel. | Separate Available now, Pilot, and Roadmap. Do not present non-working systems as equivalent capabilities. Use capability flags backed by health/configuration. | frontend/app/page.tsx capability badges; QuickStartModal categories versus defs. | Stabilization | S | TBD |  | Required
CEO-024 | The platform lacks a single primary user and hero workflow | Open | Strategy | High | P0 | The platform serves extraction, comparison, impact, requirements, change review, SAP analysis, Excel import and visualization equally. This risks perceived feature collection rather than a must-have product. | Position the hero workflow as Engineering Change and Discrepancy Review: load/resolve context, explain changes, quantify exposure, review evidence, produce actions. Other pillars are supporting capabilities. | Current pillar breadth and workspace navigation. | CEO decision | M | TBD |  | Required
CEO-025 | Source-centric information architecture obscures task outcomes | Open | Strategy | High | P1 | The workspace is organized around source cards and technical systems rather than user jobs such as review change, reconcile BOMs or investigate exposure. | Retain source onboarding but add task entry points and saved review workspaces. Sources become evidence providers inside a review, not the top-level product purpose. | frontend/app/bom-comparison/page.tsx groups by PLM/ERP/CPQ/DATA. | Platform productization | L | TBD |  | Required
CEO-026 | Client-side comparison can freeze and exposes full datasets | Open | Performance/Security | High | P0 | All loaded source structures are delivered to the browser and compared synchronously. Large BOMs risk UI stalls and unnecessary data exposure. | Introduce a worker boundary immediately for UI safety, then server-side comparison over authorized snapshots for production. Return paged summaries and on-demand branches. | page.tsx compareMultipleBoms useMemo; client-side lib/bom-comparison.ts. | Scale foundation | L | TBD |  | Required
CEO-027 | Graph views lack enforceable operating limits | Open | Performance | High | P1 | 2D and 3D include adaptive rendering, but there is no clear hard budget, fallback policy or server-side pagination for very large BOMs. | Define tested node/edge budgets. Auto-select Tree/summary mode beyond thresholds, provide sampled/LOD graph, and keep highlighted evidence at full fidelity. | BomConstellationView.tsx; BomThreeUniverseView.tsx; no enforced max structures. | Scale foundation | L | TBD |  | Required
CEO-028 | 3D error boundary provides no actionable recovery | Open | Reliability | Medium | P1 | The WebGL boundary displays only “3D rendering unavailable,” without reason, telemetry, fallback action or correlation details. | Capture render errors, log browser/GPU capability safely, provide Return to Tree and Retry 3D actions, and track 3D failure rate. | BomThreeUniverseView.tsx Boundary class. | Stabilization | S | TBD |  | Required
CEO-029 | Observability is logs, not an operational system | Open | Operations | Critical | P0 | The platform lacks demonstrated metrics, traces, dashboards, alerts and correlation across browser, Next.js, .NET, Java/Python and source systems. | Adopt OpenTelemetry correlation. Define source extraction SLIs, job age, failure codes, queue depth, payload size, normalization errors, comparison latency and client render failures. Provide dashboard, alerts and runbooks. | File-based AuditLogger and console logging; no metrics/tracing evidence. | Production gate | XL | TBD |  | Required
CEO-030 | Errors are still mapped from free-form strings | Open | Reliability | High | P0 | User-facing error improvements categorize outcomes by message and status, but connector/backend contracts do not consistently emit stable error codes. | Define versioned ErrorEnvelope with code, category, safeMessage, retryable, correlationId and technicalReference. Map source-native errors once at connector boundary. | frontend/lib/user-facing-errors.ts; route handlers return error strings. | Stabilization | M | TBD |  | Required
CEO-031 | Catch-all exception suppression risks silent data loss | Open | Reliability | Critical | P0 | Backend sample/integration code contains many catch(Exception) patterns, including ignored exceptions, which can hide partial extraction or variant-rule failures. | Eliminate empty catches. Name connector exceptions, record affected object/phase, fail or mark partial results explicitly, and add tests that prove no silent omission. | Bundle count: 80 catch(Exception variants); Teamcenter/Configit integration sources. | Production gate | L | TBD |  | Required
CEO-032 | System.exit is used in integration code | Open | Reliability | High | P0 | Connector/sample code invokes System.exit, which is unsafe when reused in a managed worker or orchestration process. | Return typed exit results from connector entrypoints. Isolate any legacy executable in a worker process and interpret exit codes centrally. | TeamCenter-to-Configit source bundle contains multiple System.exit calls. | Stabilization | M | TBD |  | Required
CEO-033 | Subprocess timeout does not provide full cancellation semantics | Open | Reliability | High | P0 | Routes set execution timeouts, but platform-wide cancellation, child-process tree termination and connector cleanup are not proven. | Implement cancellation tokens from API to worker, kill process trees, mark terminal CANCELLED/TIMED_OUT state, and clean temporary/output files idempotently. | Next.js execFile timeouts; .NET SubprocessExecutor/PipelineOrchestrator. | Architecture foundation | L | TBD |  | Required
CEO-034 | No connector circuit breaker or source throttling | Open | Reliability | High | P1 | Concurrent users can overwhelm SAP sessions, Teamcenter pools or other licensed systems, and repeated failures can amplify outages. | Add per-source concurrency limits, rate limits, circuit breakers, retry budgets and health state. Expose source availability before request submission. | Connector architecture and job orchestration; no breaker/backpressure evidence. | Production gate | L | TBD |  | Required
CEO-035 | Source requests are not proven idempotent | Open | Reliability | High | P1 | Double-clicks, retries or network ambiguity may create duplicate extraction jobs and repeated source load. | Accept an idempotency key derived from actor, source, normalized request and time window. Return existing active/succeeded snapshot when policy allows. | Forms and start endpoints; no idempotency contract visible. | Architecture foundation | M | TBD |  | Required
CEO-036 | Exports are ungoverned and unaudited | Open | Security | Critical | P0 | Client-side JSON/CSV and impact exports can create unmanaged copies of sensitive product structures without permission checks, classification or audit. | Enforce export entitlement server-side, classify/watermark reports, log actor/snapshot/purpose, set payload limits, and support disabled export policy. | ComparisonSummary.tsx; ImpactAnalysisWorkspace.tsx; client Blob downloads. | Production gate | L | TBD |  | Required
CEO-037 | Raw technical details may disclose sensitive internals | Open | Security | High | P0 | TechnicalDetails can expose backend messages to users and copy them to clipboard. Route errors can include subprocess stderr and local paths. | Return safe user messages and opaque technical reference IDs. Restrict detailed diagnostics to authorized support views and scrub paths, tokens and identifiers. | TechnicalDetails.tsx; bom-windchill route stderr tail; user-facing error mapping. | Stabilization | M | TBD |  | Required
CEO-038 | Debug response can return raw Configit data and runtime paths | Open | Security | High | P0 | The Configit route supports debug=1 and returns raw response, Python executable and script path. | Remove in production or require privileged support authorization. Redact payloads and paths, and audit access. | frontend/app/api/bom-configit/route.ts debug branch. | Stabilization | S | TBD |  | Required
CEO-039 | No payload schema validation at connector boundaries | Open | Data quality | Critical | P0 | Routes and transforms inspect unknown objects dynamically. Schema drift can silently drop fields or misclassify empty results as pending. | Use versioned JSON Schema/Zod/.NET contracts at ingress and canonical output. Reject unsupported versions with SCHEMA_UNSUPPORTED and preserve validation diagnostics. | record/asRecord dynamic parsing across routes and transforms. | Architecture foundation | L | TBD |  | Required
CEO-040 | Tree transforms do not consistently protect against cycles or extreme depth | Open | Reliability | High | P1 | Recursive transforms and searches assume acyclic reasonable-depth structures. Enterprise BOMs can contain pathological references or malformed payloads. | Normalize iteratively with visited occurrence keys, maximum depth/node budgets and explicit cycle-reference nodes. Test deep, wide and cyclic fixtures. | Recursive source transforms and find functions in frontend. | Scale foundation | M | TBD |  | Required
CEO-041 | Generated build artifacts have polluted Git history | Open | Engineering hygiene | Medium | P1 | bin/obj files appear among recently touched files and stashes despite ignore rules, indicating tracked generated artifacts. | Identify tracked build outputs, remove them from index in a dedicated hygiene commit, strengthen ignore rules, and add CI check against generated artifacts. | Audit recently touched files and three stashes. | Stabilization | S | TBD |  | Required
CEO-042 | Three stashes contain mostly generated outputs | Open | Engineering hygiene | Low | P2 | Stashes 0 and 1 appear duplicated and contain only obj files; stash 2 includes obj and extraction samples. | After a no-loss review, document hashes/file lists, archive any meaningful fixture changes, then drop generated-only stashes. | git stash file lists in source bundle. | Stabilization | S | TBD |  | Required
CEO-043 | Line-ending policy is not explicit | Open | Engineering hygiene | Medium | P1 | LF-to-CRLF warnings appear for all active frontend changes, risking noisy diffs and accidental whole-file modifications. | Add .gitattributes and EditorConfig with explicit text/eol policy, renormalize in an isolated commit, and align formatters. | Git diff warnings; no root .gitattributes/.editorconfig included. | Stabilization | S | TBD |  | Required
CEO-044 | Test coverage is far below product complexity | Open | Quality | Critical | P0 | The bundle shows one meaningful AuditLogger test and a placeholder UnitTest1, with no visible frontend unit/component/E2E suite for the primary flows. | Establish a test pyramid: adapter fixtures, canonical model, comparison benchmarks, state reducers, component states, connector contract mocks, Playwright smoke, large-BOM performance and security tests. | Orchestration.API.Tests/AuditLoggerTests.cs; UnitTest1; no frontend tests found. | Production gate | XL | TBD |  | Required
CEO-045 | There is no versioned regression corpus for matching | Open | Quality | Critical | P0 | Comparison behavior cannot be safely tuned without labeled source-pair fixtures and expected matches/differences. | Create sanitized golden datasets per source pair, including duplicate IDs, moves, units, revisions, alternates, missing fields and probable matches. Track precision/recall and false-positive budget in CI. | Comparison engine present; no benchmark fixture suite demonstrated. | Core intelligence | L | TBD |  | Required
CEO-046 | No large-BOM performance certification | Open | Quality | High | P1 | The product has performance optimizations but no evidence of repeatable budgets for 1k, 10k, 100k or larger occurrence structures. | Create synthetic and sanitized scale fixtures. Measure extraction, normalization, comparison, tree interaction, 2D, 3D, memory and export. Gate releases against budgets. | Visualization performance code; no benchmark suite included. | Scale foundation | L | TBD |  | Required
CEO-047 | Accessibility is inconsistent across advanced workspaces | Open | Quality | High | P1 | Some modals implement focus behavior, while others lack focus trapping, labels or keyboard-equivalent graph navigation. 2D/3D cannot be the only way to access evidence. | Adopt WCAG-focused component primitives, run axe in CI, guarantee Tree/table fallback, provide keyboard node navigation and announce selection/status changes. | QuickStart modal has focus trap; other overlays and graph SVG/WebGL controls vary. | Product quality | L | TBD |  | Required
CEO-048 | Modal, drawer and Escape behavior have no single interaction stack | Open | Frontend architecture | High | P1 | Fullscreen, comparison modal, requirement evolution, requirements drawer, findings, context menus and other overlays independently listen for Escape and manage z-index/body overflow. | Introduce an overlay manager with stack order, focus return, scroll lock and Escape ownership. Test nested overlay plus fullscreen behavior. | Multiple components with independent key listeners and z-index values up to 10000. | Architecture foundation | M | TBD |  | Required
CEO-049 | Comparison loader simulates work with fixed timers | Open | Product trust | Medium | P1 | The transition displays staged processing and completes after 2.2 or 3 seconds rather than reflecting actual computation progress. | Either make the transition a brief honest UI transition, or bind stages to actual worker/service events. Never imply work is occurring when it completed instantly. | frontend/components/ComparisonLoader.tsx intervals and fixed timeout. | Stabilization | S | TBD |  | Required
CEO-050 | Client saved views are browser-local and ungoverned | Open | Product | Medium | P2 | Constellation saved views live in localStorage, cannot be shared, audited or tied to a snapshot, and may become invalid when a BOM changes. | Include snapshot/version in saved view identity. For pilots, label as local; for productization, persist user-owned views with migration/version validation. | BomConstellationView.tsx localStorage saved views. | Platform productization | M | TBD |  | Required
CEO-051 | SAP impact aggregation can combine mixed currencies | Open | Product trust | Critical | P0 | Summary inventory value reduces values across returned materials and formats them using a selected/fallback currency. If materials span currencies, the total is misleading. | Group totals by currency and valuation area, or convert only with explicit dated rates. Never show one money total for heterogeneous currencies. | SapBusinessImpactPanel.tsx summary.value reduction and currency selection. | Stabilization | S | TBD |  | Required
CEO-052 | SAP polling retries all failures without classifying retryability | Open | Reliability | High | P1 | Business-impact loading retries up to 45 times for any caught error, including validation or authorization failures that should terminate immediately. | Retry only 202/404-not-ready and defined transient codes with exponential backoff and jitter. Stop on validation/auth/configuration errors and honor Retry-After. | SapBusinessImpactPanel.tsx attempt loop. | Stabilization | M | TBD |  | Required
CEO-053 | SAP business impact and BOM lifecycle can diverge | Open | Product | High | P1 | BOM structure and business-impact results are loaded through separate consumers and may reach different terminal times or partial states without a single job outcome. | Model one extraction job with named artifacts and statuses: structure, material context, inventory, valuation, warnings. Display a unified result manifest. | page.tsx SourceBomPanel plus SapBusinessImpactPanel; shared jobId but independent polling. | Architecture foundation | M | TBD |  | Required
CEO-054 | Excel corrections are not persisted as governed learning | Open | Product | Medium | P1 | Users can override mappings, but approved corrections are session-local and cannot become reusable templates or audited source-specific rules. | Save mapping profiles by organization/template signature with explicit approval, versioning and rollback. Preserve workbook fingerprint and correction rationale. | ExcelBomImportWorkspace.tsx local mapping state. | Platform productization | L | TBD |  | Required
CEO-055 | Excel hierarchy auto-detection lacks explicit ambiguity gate | Open | Product trust | High | P1 | The engine can choose a hierarchy mode by score, but high-impact ambiguity should require review rather than silently loading a plausible structure. | Define confidence/margin thresholds. When top candidates are close or root/depth differs materially, require user selection and show side-by-side evidence. | Excel engine candidates and auto mode in ExcelBomImportWorkspace. | Core intelligence | M | TBD |  | Required
CEO-056 | Windchill operations are overloaded into one GET route | Open | API design | High | P1 | Extract, versions, structure, compare, change-impact and search share query-driven GET execution, including long-running and semantically complex operations. | Split read queries from asynchronous commands. Use typed endpoints, POST job creation for expensive operations, request schemas, cancellation and idempotency. | frontend/app/api/bom-windchill/route.ts Operation union and GET handler. | Architecture foundation | L | TBD |  | Required
CEO-057 | Unsafe identifiers and product data can enter URLs and logs | Open | Security | High | P1 | Part IDs, product IDs and versions are sent in query strings, which may be retained in browser history, proxies and logs. | Use POST bodies for sensitive commands, minimize logged identifiers, apply redaction/hashing policy, and keep user-facing deep links based on internal snapshot IDs. | bom-windchill and bom-configit query parameters; frontend fetch URLs. | Production gate | M | TBD |  | Required
CEO-058 | No explicit data retention, deletion or classification controls | Open | Data governance | Critical | P0 | BOMs, requirements, inventory, valuation and change data are sensitive, but no enforceable retention, classification or deletion workflow is visible. | Classify data by source, define retention and legal requirements, encrypt snapshots, support deletion, and expose lineage. Runtime and exported copies need separate policies. | Runtime jobs, local files, exports and no persistent governance layer. | Production gate | XL | TBD |  | Required
CEO-059 | No deployment safety model or feature flags is demonstrated | Open | Operations | High | P1 | The platform integrates many connectors and experimental visualization/workflow features, but partial deployment, rollback and capability gating are not evident. | Use environment-validated configuration, connector capability flags, kill switches, canary deployment, immutable artifacts and automated rollback. | PM2/frontend and .NET project evidence; no feature flag framework found. | Production gate | L | TBD |  | Required
CEO-060 | Product metrics are feature-centric rather than outcome-centric | Open | Strategy | High | P1 | Current telemetry recommendations focus on calls and durations, but the platform has no demonstrated measurement of investigation time saved, review completion or avoided errors. | Define north-star outcomes: time to trusted change assessment, discrepancy resolution rate, manual navigation avoided, approved match rate and evidence completeness. Instrument journeys, not vanity clicks. | Current platform feature catalogue and absent product analytics evidence. | CEO decision | M | TBD |  | Required
CEO-061 | No explicit support and connector ownership model | Open | Operations | High | P1 | Failures span frontend, orchestration, Java/Python runtimes and enterprise systems, but ownership and escalation boundaries are not encoded. | Define RACI per connector and service, support hours, source-system handoff, severity policy, runbooks and correlation-ID based triage. | Multi-runtime architecture; documentation lists ownership as unresolved. | Production gate | M | TBD |  | Required
CEO-062 | The current working tree mixes unrelated change themes | Open | Engineering governance | High | P0 | SAP refinement, error handling, Excel, layout and visualization performance exist together as uncommitted work. Regression attribution and review are difficult. | After validation, split by coherent change intent without losing work. Establish a clean integration branch rule and PR-level acceptance evidence. | Git status and diff stat: 20 modified frontend files plus new feedback components. | Stabilization | M | TBD |  | Required
CEO-063 | Repository documentation contains current-state contradictions | Open | Governance | Medium | P1 | The master document contains dropped Radial references and differing Next.js versions, mixing verified, inferred and target-state claims. | Convert the master document into current state plus ADRs and roadmap. Generate stack/version sections from manifests and require evidence links for verified claims. | Master Documentation V2 and current source bundle. | Stabilization | M | TBD |  | Required
CEO-064 | No formal architecture decision record trail | Open | Governance | Medium | P1 | Major decisions such as source adapters, client-side comparison, global stores, native fullscreen and connector execution are not backed by an ADR trail. | Create concise ADRs for canonical model, job architecture, connector boundary, identity policy, overlay ownership, snapshot storage and AI governance. | No ADR directory or decision records identified in bundle. | Architecture foundation | M | TBD |  | Required
CEO-065 | AI readiness depends on unresolved deterministic foundations | Open | Strategy | High | P0 | AI can amplify comparison and change review, but weak identity, provenance, permissions, snapshot reproducibility and evidence contracts would make answers unsafe or untrustworthy. | Treat canonical snapshots, evidence citations, authorization, typed tool APIs and evaluation fixtures as prerequisites. Keep deterministic results usable when AI is absent. | Current AI direction plus platform gaps in identity, auth and persistence. | CEO decision | L | TBD |  | Required

## Design Bugs
ID | Title | Status | Area | Design_Dimension | Severity | Priority | Description | Recommended_Solution | Evidence | Action | Effort | Owner | Dependencies | Acceptance_Criteria
DES-001 | Workspace begins with systems instead of user intent | Closed | Workspace | Information architecture | Critical | P0 | The primary workspace asks users to add PLM, ERP, CPQ, or DATA sources before establishing the task being performed. This makes the product feel like an integration console rather than a decision workspace. | Add task entry points: Review a change, Reconcile BOMs, Investigate a material, and Import external BOM. Preserve Add source as a secondary expert action. | app/bom-comparison/page.tsx; QuickStartModal.tsx | Do now | L | TBD |  | A first-time user can identify the appropriate starting action within 5 seconds without knowing source-system categories.
DES-002 | No persistent review context or investigation title | Closed | Workspace | User journey | High | P0 | A session has no visible name, purpose, owner, timestamp, or review phase. Users cannot tell what investigation they are conducting once several sources are loaded. | Introduce a compact Review Header containing title, objective, product/change context, saved state, owner, and last refresh. | app/bom-comparison/page.tsx | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-003 | Source cards dominate the experience after data is loaded | Closed | Workspace | Visual hierarchy | High | P0 | The same source form and card framing remain visually prominent after extraction, even when the user should focus on evidence and decisions. | Collapse successful source setup into a compact source strip. Promote the active analysis workspace and keep re-run/edit controls in source details. | page.tsx; SourceBomPanel.tsx | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-004 | Source grouping creates excessive horizontal navigation | Closed | Workspace | Responsive design | High | P0 | PLM/ERP/CPQ/DATA groups use horizontal overflow and snap behavior. Multiple source cards can require wide canvases and unintuitive sideways movement on standard laptops. | Use a source rail plus one central investigation canvas. For side-by-side comparison, let users choose 2-column or synchronized stacked mode. | page.tsx; globals.css bom-source-group rules | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-005 | Empty workspace is visually empty but not instructive | Closed | Workspace | Interaction states | High | P0 | The initial workspace displays a large dashed area with only a plus button. It does not explain the available workflows, prerequisites, or example outcome. | Create a task-based empty state with one primary action, three common workflows, a recent review section, and source readiness status. | page.tsx empty active state | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-006 | Home page promise is broader than available experience | Closed | Home | Product trust | High | P0 | ALM, Oracle, and Servigistics are visually presented alongside working capabilities, which can imply parity and availability. | Label each capability Available, Pilot, or Roadmap. Make unavailable cards informational rather than equivalent entry points. | app/page.tsx; QuickStartModal categories | Do now | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-007 | Homepage card grid is generic and product-light | Closed | Home | Visual hierarchy | Medium | P1 | Five equal capability cards and a decorative orbit visual communicate categories but not the differentiated engineering workflow. | Replace capability cards with a concrete change-review story: change evidence, affected systems, exposure, and action. Use the platform visual as process evidence, not decoration. | app/page.tsx PlatformVisual and capability cards | Defer | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-008 | Hero typography is too large and brittle | Closed | Home | Responsive design | Medium | P1 | The fixed text-7xl heading and five-column card grid can become cramped at laptop widths and are not designed for smaller screens. | Use a fluid type scale, breakpoint-specific card count, and content-priority rules. Validate at 1280x720, 1366x768, 1440x900, and 1920x1080. | app/page.tsx heading and grid-cols-5 | Do now | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-009 | The visual design system is implicit, not governed | Closed | Platform-wide | Design system | High | P0 | Colors, radius, text sizes, shadows, overlays, and semantic states are repeated as local utility strings. Similar patterns have subtle differences. | Create DESIGN.md plus semantic tokens for surfaces, text, border, focus, status, evidence type, density, radii, elevation, and motion. | Widespread Tailwind literals across components | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-010 | Excessive rounded containers reduce hierarchy | Closed | Platform-wide | Visual hierarchy | Medium | P1 | Nested 22px to 30px rounded cards make forms, source groups, panels, notices, and workspaces visually equivalent. | Reserve large radii for page-level containers, medium radii for panels, and small radii for controls. Remove a container layer wherever grouping is already clear through spacing. | page.tsx; SourceBomPanel; forms; modals | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-011 | Cyan is overused as brand, action, selection, focus, and information | Closed | Platform-wide | Design system | High | P1 | One accent color carries too many meanings, reducing semantic clarity and making active states, information, links, and brand treatment compete. | Define semantic roles: primary action, selection, information, evidence, focus ring, and link. Keep cyan as brand/primary while using distinct restrained tokens for other meanings. | globals.css and component utility classes | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-012 | Tiny text is used for meaningful engineering controls | Closed | Platform-wide | Accessibility | Critical | P0 | Many controls and evidence labels use 6px to 10px text, including graph toolbars, metrics, details, findings, and status. This harms readability and accessibility. | Set 12px as the minimum for essential controls and metadata, 14px for body/evidence, and 16px for inputs. Permit 10px only for nonessential uppercase overlines. | BomConstellationToolbar; BomThree*; RequirementsExplorerModal; SourceBomPanel | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-013 | Dark mode is treated as the primary specialist workspace style | Closed | Platform-wide | Visual hierarchy | Medium | P1 | Complex workspaces use near-black surfaces almost universally, producing high visual density and making borders/status colors carry too much structure. | Define a true enterprise light workspace and a quieter dark mode. Use neutral elevation and spacing before border proliferation. | Visualization, SAP, Excel, requirements and review components | Defer | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-014 | Status labels expose implementation state rather than user state | Closed | Source panel | Content design | Medium | P1 | The panel header displays idle, loading, ready, empty, or error as raw status words. These labels are technically correct but not always meaningful. | Use contextual copy such as Not started, Extracting, Structure ready, No maintained BOM, or Connection failed, plus timestamp and source. | SourceBomPanel.tsx status header | Do now | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-015 | Source panel header does not identify snapshot context | Closed | Source panel | Product trust | Critical | P0 | Once loaded, the panel does not prominently show revision/configuration/plant/date and extraction time. Users can compare visually incompatible snapshots. | Add a snapshot context bar with source, object, revision/configuration, plant, effective date, extraction time, and freshness state. | SourceBomPanel.tsx; source forms | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-016 | Toolbar mixes view, analysis, and navigation controls | Closed | Source panel | Information architecture | High | P0 | Expand/collapse, fullscreen, impact, trace, requirements, and view-switching live at the same toolbar level. The high-frequency view controls compete with advanced analysis modes. | Separate into View controls, Analysis modes, and More. Keep search and view switch persistent; move less frequent capabilities into an Analysis menu or contextual rail. | SourceBomPanel.tsx ready toolbar | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-017 | View switcher uses icon-only controls with delayed explanation | Closed | Source panel | Accessibility | High | P1 | 2D and 3D modes appear as icons and tooltips. The current tree state has no explicit selected tab. | Use a labeled segmented control Tree ¦ 2D ¦ 3D at ordinary widths and responsive icon labels only when space-constrained. | BomViewSwitcher.tsx | Do now | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-018 | Tree row is overloaded with badges and competing highlights | Closed | Tree | Visual hierarchy | High | P0 | Selection, comparison, impact, requirement focus, and Windchill change states can all affect row color, border, ring, side marker, badge, and text. Precedence is implicit. | Define a state precedence matrix. Use one base row state, one evidence marker rail, and one compact status group. Provide a legend when overlays are active. | SourceBomPanel.tsx TreeRow | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-019 | Tree selection opens different experiences depending on hidden modes | Closed | Tree | Interaction design | High | P0 | Selecting a row can open comparison reasoning, run impact search, run requirement trace, or show details depending on global toggles. The click affordance does not communicate this. | Make row selection stable. Put mode-specific actions in a contextual details pane, or visibly announce the active mode and resulting action before selection. | SourceBomPanel select() | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-020 | Selected node details are too shallow outside specialist modes | Closed | Tree | User journey | Medium | P1 | The standard details panel shows name and direct-child count but does not expose source attributes, provenance, path, quantity, revision, or copy actions. | Create one reusable Node Inspector with Overview, Source fields, Evidence, and Relationships sections. Use the same inspector in Tree, 2D, and 3D. | SourceBomPanel Details component | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-021 | Tree search doubles as hidden filtering infrastructure | Open | Tree | Interaction states | Medium | P1 | SearchTerm encodes search, comparison filter, and change filter in a delimited string passed to react-arborist. The UI gives limited indication when other filters hide rows. | Show active filter chips and result count. Separate search query from filter state and provide Clear all filters. | SourceBomPanel term/searchMatch | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-022 | Comparison setup begins only after sources are independently loaded | Open | Comparison | User journey | Medium | P1 | Users must understand the workspace model, add sources, run extracts, then discover Compare BOMs. There is no guided compare workflow. | Add Reconcile BOMs as a task flow that asks for primary/secondary sources, extraction contexts, and readiness in one guided sequence. | page.tsx; ComparisonSetupModal.tsx | Defer | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-023 | Comparison transition simulates work with fixed timing | Open | Comparison | Product trust | High | P0 | The loader displays staged normalization and matching messages for a fixed duration, regardless of actual calculation. | Use an honest short transition or bind progress to actual compute events. Avoid artificial claims such as evaluating hierarchy if work is already complete. | ComparisonLoader.tsx | Do now | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-024 | Comparison summary emphasizes counts before business meaning | Open | Comparison | Information architecture | High | P1 | Status filters and exports lead the summary, while the most consequential changes and confidence risks are not surfaced first. | Lead with headline findings: unresolved probable matches, changed assemblies, quantity/revision deltas, and source coverage. Keep filters secondary. | ComparisonSummary.tsx | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-025 | Comparison status colors depend too heavily on hue | Open | Comparison | Accessibility | High | P0 | Matched, changed, missing, source-only, and probable states are distinguished primarily by green, amber, rose, sky, and violet. | Pair color with icon, label, border pattern, and accessible legend. Validate colorblind palettes and contrast in light/dark modes. | ComparisonSummary; ComparisonReasoningModal; TreeRow; graph views | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-026 | Comparison explanation is comprehensive but verbose for repeated use | Open | Comparison | Content design | Medium | P1 | The modal includes summary, metrics, reasons, differences, field groups, and counterpart information. Frequent reviewers may need faster scanning. | Use a two-level layout: decision summary and key differences first; expand methodology and all matched fields on demand. | ComparisonReasoningModal.tsx | Defer | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-027 | Multi-source comparison lacks source-pair navigation | Open | Comparison | Information architecture | High | P1 | When more than two sources are included, the primary map aggregates severity but users cannot easily switch pair context or understand which source caused a status. | Add pair tabs or a source matrix, with per-source status and confidence visible in the node inspector. | ComparisonSummary; comparison map usage in SourceBomPanel | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-028 | Comparison filters can hide structural context | Open | Comparison | Interaction design | High | P1 | Filtering to changed/missing nodes through tree search may hide ancestors needed to understand hierarchy and location. | Preserve ancestor paths and show hidden descendant counts. Offer Results only and Results with context modes. | SourceBomPanel searchMatch with comparisonFilter | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-029 | SAP request scope labels are not outcome-oriented enough | Open | SAP | Content design | Medium | P1 | BOM structure and Business impact are technically accurate, but the user may not understand whether business impact includes structure or why one should be chosen. | Use Structure only and Structure + stock/cost exposure with concise consequence copy and expected time. | SAPForm.tsx | Do now | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-030 | SAP result hierarchy is long and scroll-heavy | Open | SAP | Information architecture | High | P1 | Summary, material carousel, context cards, stock/inventory/cost cards, reconciliation, locations, and warnings create a very long page inside a source card. | Use a summary header plus tabs: Overview, Stock, Valuation, Locations, Raw evidence. Keep material selection sticky. | SapBusinessImpactPanel.tsx | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-031 | SAP material carousel is inefficient for many materials | Open | SAP | Responsive design | High | P1 | Horizontal material cards work for a few items but become difficult to scan, filter, and compare at scale. | Use a searchable material table/list with status, stock, value, warning indicators, and a details pane. | SapBusinessImpactPanel materials overflow-x-auto | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-032 | SAP money totals can visually imply stronger certainty than data supports | Open | SAP | Product trust | Critical | P0 | Inventory value, valuation coverage, and reconciliation look authoritative even when results are partial or currencies/valuation contexts differ. | Place freshness, currency/valuation context, coverage, and partial-data state adjacent to totals. Disable aggregate totals when contexts are incompatible. | SapBusinessImpactPanel summary and partial warning | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-033 | SAP warnings are humanized but detached from affected fields | Open | SAP | Interaction states | Medium | P1 | Warnings are grouped at the bottom, making it difficult to connect missing optional data with specific blank values. | Annotate affected cards/fields inline and keep a consolidated warning log for support. | SapBusinessImpactPanel Warnings and Not available fields | Defer | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-034 | Excel import is powerful but presents too much at once | Open | Excel | Information architecture | High | P0 | Workbook summary, detection, mapping, normalized preview, tree preview, diagnostics, issues, and load controls create a long expert interface. | Define a three-step guided review: Understand, Resolve ambiguity, Load and inspect. Keep expert diagnostics behind Advanced. | ExcelBomImportWorkspace.tsx | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-035 | Excel auto-detection confidence lacks comparison context | Open | Excel | Product trust | High | P0 | A single confidence percentage does not explain whether competing hierarchy modes were close or materially different. | Show the selected interpretation, runner-up, score margin, expected roots/depth, and why review is required. | DetectionSummary; hierarchyCandidates | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-036 | Excel mapping controls do not distinguish required by hierarchy | Open | Excel | Interaction design | Medium | P1 | Only Item ID is globally marked required, while specific hierarchy modes may depend on level, parent, child, path, or level columns. | Update required indicators dynamically by selected hierarchy and explain which missing mapping blocks loading. | ExcelBomImportWorkspace requiredFields | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-037 | Excel preview tables need sticky headers and row focus | Open | Excel | Responsive design | Medium | P1 | The wide normalized preview is horizontally scrollable, but header and source row context can be lost during review. | Use sticky headers and first columns, row issue markers, and direct navigation from issue groups to affected rows. | Excel normalized preview table | Defer | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-038 | Windchill change review is hidden behind source-specific actions | Open | Windchill | Information architecture | High | P0 | Revision comparison and Change Notice review are initiated from Windchill form controls and conditionally open a specialist workspace, making discovery and state continuity weak. | Expose Change Review as a task and persistent workspace tab once a Windchill structure is loaded. Preserve selections when closing/reopening. | page.tsx WindchillForm and WindchillChangeReviewWorkspace | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-039 | Windchill loading and error states use a separate state model | Open | Windchill | Interaction states | High | P1 | Revision and change operations maintain independent loading/error fields outside the shared outcome system, creating inconsistent presentation. | Adopt shared async operation states and OutcomeNotice patterns with correlation references and retry scope. | page.tsx wcVersionLoading/wcRevisionError/wcChangeError | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-040 | Requirements Explorer uses browser-wide global ownership workaround | Open | Requirements | Interaction design | High | P0 | The drawer is mounted from repeated source panels and elects one active owner. Visual behavior depends on mount order rather than explicit workspace ownership. | Mount one global drawer in the page-level overlay host and give it stable focus, scroll-lock, Escape, and return-focus behavior. | RequirementsExplorerModal activeOwner; SourceBomPanel overlayOwner | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-041 | Requirements look authoritative despite simulated/local provenance | Open | Requirements | Product trust | Critical | P0 | The interface presents revisions, status, authors, dates, direct links, and corresponding parts without a persistent demo/simulated provenance treatment. | Add a prominent provenance banner and Evidence type label. Distinguish sourced links, deterministic correspondence, and simulated examples. | Requirements components and local requirement data | Do now | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-042 | Requirements drawer filter layout is mathematically inconsistent | Open | Requirements | Responsive design | Medium | P1 | The filter container combines flex, grid, and grid-cols-3 while rendering more than three source buttons plus Latest only. This is likely unpredictable across widths. | Use a documented responsive filter pattern: scrollable chips or a filter menu with selected chips. | RequirementsExplorerModal filter classes | Do now | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-043 | Requirement selection and expansion are conflated | Open | Requirements | Interaction design | Medium | P1 | Choosing a requirement activates trace focus and sets it expanded, while the row also uses expanded/collapse language. Users cannot inspect details without affecting the BOM. | Separate Inspect details from Trace in BOMs. Make trace activation an explicit action. | RequirementsExplorerModal activate and expandedId | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-044 | Impact mode produces a fixed bottom workspace that can obscure content | Open | Impact | Overlay behavior | High | P0 | ImpactAnalysisWorkspace is fixed near the bottom with high z-index, potentially covering source panels and conflicting with other overlays. | Move impact results into the shared inspector/right rail or a global analysis drawer managed by the overlay stack. | ImpactAnalysisWorkspace.tsx fixed aside | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-045 | Impact result export has no visible scope confirmation | Open | Impact | Product trust | Medium | P1 | Copy/JSON actions export the current result immediately without previewing included sources, identifiers, or sensitivity. | Add a scope summary and governed export action. For simple copy, show what was copied and source count. | ImpactAnalysisWorkspace.tsx | Defer | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-046 | 2D Constellation opens with excessive simultaneous chrome | Open | 2D Constellation | Visualization usability | Critical | P0 | Lens selector, toolbar, mode hint, search navigator, difference navigator, change rail, details, breadcrumbs, minimap, findings, requirements card, context menu, basket, and saved views can coexist. | Define a visualization chrome budget. Keep navigation, lens, and inspector persistent; place settings and advanced tools in one drawer; enforce mutual exclusivity for secondary panels. | BomConstellationView.tsx and toolbar components | Do now | XL | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-047 | 2D interaction modes are expert-first | Open | 2D Constellation | User journey | High | P0 | Pointer, hand, box select, keyboard shortcuts, pinning, history, tour, isolation, edge modes, depth, density, and saved views are exposed before users learn the graph. | Default to direct manipulation: drag background to pan, wheel to zoom, click to inspect, Shift-click for multi-select. Hide explicit modes until advanced selection is needed. | BomConstellationToolbar.tsx; BomConstellationView.tsx | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-048 | 2D lens behavior changes multiple hidden settings | Open | 2D Constellation | Interaction design | High | P1 | Selecting a lens changes color, size, labels, visibility, and panels. Users may not understand why the graph appearance changed or how to return. | Show lens description and active encoding legend. Provide Reset lens settings and clearly distinguish preset from user overrides. | BomConstellationView applyLens | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-049 | 2D labels do not guarantee readable collision behavior | Open | 2D Constellation | Visualization usability | High | P1 | Label visibility is priority-based, but labels can overlap in dense structures and density is expressed as an abstract percentage. | Use collision-aware label placement, semantic zoom, and named density levels: Minimal, Balanced, Detailed. | GraphNode label logic; labelDensity | Defer | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-050 | 2D minimap viewport calculation is difficult to trust | Open | 2D Constellation | Visualization usability | Medium | P1 | The minimap viewport rectangle approximates transform state and can exceed or misrepresent the actual screen window. | Use a tested viewport transform, clamp dimensions, and support clicking/dragging the minimap to navigate. | BomConstellationMinimap.tsx | Defer | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-051 | 2D findings and node details compete for the same lower corners | Open | 2D Constellation | Overlay behavior | High | P1 | Hover details, selected node details, findings, minimap, breadcrumbs, and change controls use fixed corners and can collide. | Adopt a layout grid with reserved top bar, left navigator, right inspector, and bottom breadcrumb zones. Secondary panels replace one another. | BomConstellationView absolute overlays | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-052 | 3D is presented as a peer view without readiness warning | Open | 3D Universe | Product trust | High | P0 | 3D is available alongside 2D even though browser/GPU capability, large-BOM readability, and accessibility vary significantly. | Treat 3D as an optional spatial investigation mode. Run capability check, show node budget, and preserve an immediate return to Tree/2D. | BomViewSwitcher; BomThreeUniverseView | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-053 | 3D controls are discoverable only through panels and hover | Open | 3D Universe | Accessibility | Critical | P0 | Orbit interaction, node selection, double-click expansion, search focus, and camera behavior lack a complete keyboard and non-WebGL equivalent within the mode. | Provide keyboard node navigation, camera reset/fit shortcuts, an accessible parallel node list, and screen-reader status updates. | BomThreeUniverseView and drei OrbitControls | Do now | XL | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-054 | 3D depth and occlusion can hide important evidence | Open | 3D Universe | Visualization usability | High | P0 | Fog, perspective, labels, and spatial layout can obscure nodes, especially when comparison/requirements/change overlays are active. | Use guided focus, depth fading aligned with selection, orthographic option, guaranteed highlighted-node visibility, and a visible legend. | Scene fog, layout and Node3 behavior | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-055 | 3D findings and change controls overlap global visualization hierarchy | Open | 3D Universe | Overlay behavior | High | P1 | Findings, change controls, lens selector, toolbar, search, difference navigator, breadcrumbs, node details, and requirement card all float independently. | Use the same visualization shell as 2D with one shared inspector and one secondary drawer. | BomThreeUniverseView composition | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-056 | 3D failure state is a dead end | Open | 3D Universe | Interaction states | High | P0 | The error boundary only displays “3D rendering unavailable.” There is no recovery, fallback, or reason. | Provide Retry 3D, Return to 2D, capability information, and a support reference. Never replace accessible evidence with an error-only canvas. | BomThreeUniverseView Boundary | Do now | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-057 | Fullscreen has no explicit layout contract | Open | Platform-wide | Responsive design | High | P0 | Native fullscreen expands the panel, but every overlay and fixed control retains its own positioning and z-index assumptions. | Define a fullscreen shell with explicit header, canvas, inspector, overlay portal, safe areas, and Escape behavior. Test nested overlays. | useBomNativeFullscreen; SourceBomPanel; visualization overlays | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-058 | Overlay z-index values form an unmanaged escalation ladder | Open | Platform-wide | Overlay behavior | Critical | P0 | Components use z-index values from 40 through 10,000 and independently manage scroll lock, portals, fixed positioning, and Escape. | Create one OverlayManager with levels for popover, drawer, modal, blocking transition, and toast. Enforce one focus owner and return-focus behavior. | QuickStart, comparison modals, requirements, impact, visualization panels | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-059 | Focus trapping is inconsistent | Open | Platform-wide | Accessibility | Critical | P0 | QuickStart implements a basic focus trap, while other dialogs and drawers often only listen for Escape or do not restore focus. | Use accessible dialog/drawer primitives with consistent initial focus, trap, labelled description, inert background, and focus return. | QuickStartModal compared with AddComparisonSourceModal and specialist overlays | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-060 | Touch targets and icon buttons are inconsistently labelled | Open | Platform-wide | Accessibility | High | P1 | Some controls have aria-label/title while others are bare icon buttons or rely on hover-only tooltips. | Require accessible name, 40px minimum target, visible focus, and non-hover discovery for every icon action. Add lint/test coverage. | Multiple toolbars, modals, details panels | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-061 | Reduced-motion support exists but visualization motion remains conceptually heavy | Open | Platform-wide | Accessibility | Medium | P1 | Global CSS suppresses animation duration, but continuous graph pulses, tours, camera movement, and progress transitions need behavior-level alternatives. | Disable tours/pulses, use instant camera transitions, and avoid animated-only state communication under reduced motion. | globals.css; Constellation tour; Node3 pulse; camera rig | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-062 | Responsive strategy does not define minimum viable workflow per viewport | Open | Platform-wide | Responsive design | High | P0 | The current strategy fits controls with wrapping, hiding labels, and horizontal scrolling but does not specify which tasks are supported on phone, tablet, laptop, and desktop. | Define viewport contracts. Phone: review summary and decisions. Tablet: Tree/details. Laptop/Desktop: full comparison and 2D/3D investigation. Communicate unsupported modes honestly. | globals.css container queries; complex specialist workspaces | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-063 | No visual regression or design acceptance suite is evident | Open | Platform-wide | Design system | Critical | P0 | The branch changes many high-risk visual surfaces without screenshot baselines or acceptance scenarios. | Add Storybook or equivalent states, Playwright visual snapshots, axe checks, and responsive captures for all shared components and hero journeys. | No frontend test files visible in source bundle | Do now | XL | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-064 | Error messaging is improved but support escalation is incomplete | Open | Platform-wide | Interaction states | High | P1 | User-facing errors provide friendly copy and optional technical details, but there is no consistent correlation ID, support action, or distinction between user-fixable and administrator-fixable failures. | Design an error taxonomy with next best action, retry policy, admin contact/escalation, and copyable support reference. | user-facing-errors.ts; OutcomeNotice; TechnicalDetails | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-065 | Toast usage duplicates inline outcome states | Open | Platform-wide | Interaction states | Medium | P1 | Forms and panels often show toast plus inline error or notice, creating duplicate announcements and potential screen-reader noise. | Use toasts for global transient confirmation only. Keep operation-specific errors and partial outcomes inline at the point of action. | Forms; SourceBomPanel; SAP and Excel panels | Do now | S | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-066 | Success states do not consistently show freshness and next action | Open | Platform-wide | Interaction states | Medium | P1 | Success toasts say structure ready, but loaded panels do not consistently display extraction time, freshness, expected next step, or save status. | Add result manifests and contextual next actions: Compare, Review changes, Analyze exposure, Save snapshot. | SourceBomPanel; page.tsx success callbacks | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-067 | Long names and identifiers are often truncated without recovery | Open | Platform-wide | Edge cases | High | P1 | Source cards, material cards, breadcrumbs, graph labels, and headers truncate names, but full value is not always accessible by keyboard or copy. | Provide accessible title/description, copy action, and details pane. Never make hover tooltip the only access to full identifiers. | page.tsx; SAP cards; breadcrumbs; graph labels | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-068 | No stale-data or source-disconnected visual state | Open | Platform-wide | Product trust | Critical | P0 | Loaded data remains visually ready even if source connectivity changes, the session ages, or a more recent revision exists. | Show snapshot timestamp and freshness; detect source disconnect; mark stale results without deleting them; provide Refresh with context. | SourceBomPanel; source operation flows | Defer | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-069 | No consistent destructive-action confirmation model | Open | Platform-wide | Interaction design | High | P1 | Removing a source can terminate an active comparison and clear related state immediately. Resetting Excel also clears the imported structure. | Warn when an action invalidates comparison, impact, review, or unsaved corrections. Provide undo for reversible removal. | page.tsx remove(); Excel reset() | Do now | M | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.
DES-070 | Design review decisions are not traceable to reusable patterns | Open | Governance | Design system | High | P1 | Improvements are currently applied locally across components, increasing the chance that new pillars repeat old mistakes. | Create component and pattern ownership: WorkspaceShell, SourceSetup, AsyncOutcome, Inspector, Overlay, EvidenceBadge, SnapshotContext, VisualizationShell, and DataTable. | Current repeated component structures | Do now | L | TBD |  | Reviewed in implementation and verified through the relevant usability, accessibility, responsive, and regression checks.

## Dev
Tasks | Status | Remarks
SAP Change management | In Progress | Change object to be brought to Platform
Single Workspace (MAIN PRIORITY) | In Progress | Separate Page is built and is able to fetch products from different platforms in a single search Looking into how we can extract via single name from all enterprise applications(for SAP CONFIGIT AND TC)
Resolve Design Flaws | In Progress | solved 11/70 bugs
Resolve Engineering Bugs | In Progress
Resolve Architectural Bugs | In Progress
Improvization visualisation for Huge BOMs (2ND PRIORITY) | In Progress
Bring Service BOM via Excel/ Windchill | In Progress | Propogate to all parts to create service BOM
Bring Supplier/Procurements Parts | Yet to Start
Bring Requirement Parts with electrical/software parts | Yet to Start | Parts created in Windchill
host it on our Remote Server | Yet to Start
Create Supplier and Procurement Parts | Yet to Start

## Application Flaws
ID | Title | Status | Slice | Review_Section | Severity | Priority | Description | Opinionated_Recommendation | Tradeoffs | Evidence | Action | Effort | Owner | Dependencies | Acceptance_Criteria
ENG-001 | Split mixed branch into four reviewable changes | Open | Cross-cutting | Architecture | Critical | P0 | The branch combines feedback infrastructure, SAP contracts, SAP presentation, and visualization behavior across 23 changed files. | Preserve the current work, then split commits and review gates by the four agreed slices. Do not rewrite or discard working code. | More commits and temporary integration overhead, but substantially lower regression and rollback risk. | Branch audit: 23 changed files, 349 insertions, 7,790 deletions. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-002 | Define an integration contract between the four slices | Open | Cross-cutting | Architecture | High | P0 | The slices share SourceBomPanel, page orchestration, API types, and user outcomes. Without explicit boundaries, splitting commits alone will not isolate behavior. | Create a small contract document covering request, job status, artifact manifest, normalized error, and UI consumption. | Adds up-front contract work; avoids implicit coupling and divergent assumptions. | page.tsx; SourceBomPanel.tsx; lib/api.ts; feedback components. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-003 | Establish a no-regression baseline before refactoring | Open | Cross-cutting | Tests | Critical | P0 | Current automated coverage is insufficient to prove that source extraction, comparison, SAP impact, and visualizations still work after separation. | Capture sanitized golden payloads, expected normalized roots, screenshots, and smoke flows before structural changes. | Costs several days; prevents silent loss of scarce connector behavior. | AuditLoggerTests only meaningful backend test; UnitTest1 placeholder; no frontend suite visible. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-004 | Large page component is an orchestration hotspot | Open | Cross-cutting | Architecture | High | P0 | bom-comparison/page.tsx owns source instances, forms, extraction callbacks, Windchill revision/change operations, comparison, and specialist workspaces. | Introduce explicit hooks/reducers by lifecycle: useSourceWorkspace, useComparisonSession, useWindchillReview, and useSapJob. Keep the page as composition, not business orchestration. | Adds modules, but makes changes testable and reduces accidental state resets. | frontend/app/bom-comparison/page.tsx. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-005 | SourceBomPanel violates single-responsibility boundaries | Open | Cross-cutting | Architecture | Critical | P0 | The panel fetches/polls data, transforms payloads, manages tree state, visualization modes, comparison, impact, requirements, fullscreen, and global overlays. | Use SourceBomPanel as a shell. Move runtime lifecycle to a controller hook, transformation to adapters, and global overlays to the page. | Moderate migration complexity; materially reduces blast radius and duplicate lifecycle behavior. | frontend/components/SourceBomPanel.tsx. | Do now | XL | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-006 | Canonical TreeNodeData is used as transport, domain, and view model | Open | Cross-cutting | Architecture | Critical | P0 | A permissive tree model with free-form attributes carries source identity, occurrence data, comparison fields, and visualization state. | Introduce a versioned CanonicalBomSnapshot and project it to TreeNodeData for existing UI compatibility. Keep the compatibility projection until all consumers migrate. | Temporary dual-model complexity; necessary for provenance, occurrence identity, units, revision context, and reproducible comparison. | types/bom-comparison.ts and source transforms. | Do now | XL | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-007 | No feature-flag boundary for risky cross-cutting behavior | Open | Cross-cutting | Reliability | High | P1 | New SAP and visualization behavior can become active globally when merged. | Gate new SAP impact contract and visualization enhancements independently by environment/configuration. Include kill switches. | Adds configuration paths; makes rollout and rollback reversible. | Current branch integration and PM2/deployment context. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-008 | Generated/runtime artifacts contaminate engineering state | Open | Cross-cutting | Code Quality | High | P0 | Runtime SAP job folders and generated build artifacts appear in repository history/stashes. | Remove tracked generated artifacts in a dedicated hygiene commit, move runtime output outside the repo, and add CI checks. | One-time cleanup can create noisy diffs; afterward improves review quality and portability. | SAP-BOM-Extractor/runtime/jobs; bin/obj history/stashes. | Do now | S | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-009 | Line-ending normalization is unresolved | Open | Cross-cutting | Code Quality | Medium | P1 | Repeated LF-to-CRLF warnings can disguise whole-file changes and complicate commit splitting. | Add .gitattributes and EditorConfig, then renormalize in an isolated commit before behavioral review. | Creates one noisy mechanical commit; subsequent diffs become trustworthy. | Git diff warnings in audit. | Do now | S | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-010 | No ADR trail for key integration decisions | Open | Cross-cutting | Code Quality | Medium | P1 | Job execution, source adapter boundaries, client comparison, singleton stores, and visualization ownership are undocumented decisions. | Add concise ADRs for job/artifact model, canonical snapshot, connector execution, overlay ownership, and client/server comparison boundary. | Small documentation burden; prevents architecture from reverting through local fixes. | No ADR directory identified. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-011 | Error normalization is string-driven | Open | Slice 1: Shared outcomes | Architecture | High | P0 | User-facing errors infer categories from status codes and message text. Backend wording changes can alter UX and retry behavior. | Define a versioned ErrorEnvelope with code, category, safeMessage, retryable, correlationId, and technicalReference. Normalize once at the boundary. | Requires backend/frontend coordination; removes brittle message parsing. | frontend/lib/user-facing-errors.ts; API routes returning strings. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-012 | Outcome components lack a discriminated state contract | Open | Slice 1: Shared outcomes | Code Quality | High | P1 | OutcomeNotice and TechnicalDetails are presentation components, but callers can combine severity, title, message, retry, and details inconsistently. | Use a discriminated AsyncOutcome type for validation, connection, configuration, not-found, timeout, partial, and unexpected states. | More explicit types and mapping code; fewer impossible UI states. | components/feedback/* and form integrations. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-013 | Technical details may leak paths and subprocess output | Open | Slice 1: Shared outcomes | Reliability | Critical | P0 | Raw stderr, script paths, Python executable paths, identifiers, or internal errors can reach technical details and clipboard. | Return a safe support reference by default. Restrict sanitized diagnostics to authorized support mode. | Reduces immediate debugging detail for ordinary users; significantly improves security and portability. | TechnicalDetails.tsx; Configit/Windchill API route debug behavior. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-014 | Toast and inline error channels can duplicate events | Open | Slice 1: Shared outcomes | Code Quality | Medium | P1 | The same operation can produce form error state, panel notice, and toast, creating duplicate announcements and divergent clearing behavior. | Define an ownership rule: inline for local operations, panel for artifact state, toast only for global transient confirmation. | Requires updating callers; simplifies screen-reader and state behavior. | Forms, SourceBomPanel, SAP/Excel workspaces. | Do now | S | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-015 | Retry behavior is not encoded in the error contract | Open | Slice 1: Shared outcomes | Reliability | High | P0 | Retry buttons can be shown based on local assumptions rather than stable upstream retryability. | Make retryable and retryAfter first-class fields. Log every retry with prior correlation ID and attempt number. | Backend must classify failures accurately; prevents retries of authorization and validation errors. | user-facing-errors.ts and retry integrations. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-016 | No correlation ID propagation across runtimes | Open | Slice 1: Shared outcomes | Architecture | Critical | P0 | Browser, Next.js, .NET, Python/Java connector, and source logs cannot be reliably joined for one failed request. | Generate or accept a correlation ID at ingress and propagate it through headers, job records, subprocess environment, artifact manifest, audit logs, and UI support reference. | Touches multiple layers; provides the highest operational leverage. | Multi-runtime pipeline and file-based audit logging. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-017 | Outcome mapping lacks contract tests | Open | Slice 1: Shared outcomes | Tests | Critical | P0 | There is no visible table-driven suite proving every backend error code maps to the intended message, retry policy, and technical reference. | Create table-driven unit tests plus component tests for every outcome category, including unknown codes and malformed envelopes. | Adds many small tests; stabilizes a shared cross-platform dependency. | No frontend tests visible. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-018 | Partial success is not a first-class shared outcome | Open | Slice 1: Shared outcomes | Architecture | High | P0 | SAP and connector workflows can yield useful artifacts plus warnings, but the shared outcome layer mainly models success/error/warning presentation. | Model job outcome separately from artifact outcomes. A job can complete with available, unavailable, stale, or failed artifacts. | Slightly richer state model; avoids discarding valid results or pretending full success. | SAP structure/impact independent retrieval; OutcomeNotice. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-019 | Error details are not bounded for rendering or logging | Open | Slice 1: Shared outcomes | Performance | Medium | P1 | Large stderr, raw response, or nested diagnostics can inflate payloads and freeze copy/render operations. | Bound diagnostic size, redact secrets, preserve full detail in protected logs, and return a truncation indicator. | Support may need log access for full detail; browser remains safe. | Route stderr tails, raw debug response, max buffers. | Do now | S | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-020 | Shared outcome infrastructure has no accessibility tests | Open | Slice 1: Shared outcomes | Tests | High | P1 | Alerts, retry buttons, technical-detail expansion, focus, and screen-reader announcement behavior are not verified. | Add axe and keyboard tests for alert roles, live regions, expansion, focus return, and duplicate announcement prevention. | Adds test setup; prevents cross-platform accessibility regressions. | OutcomeNotice and TechnicalDetails. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-021 | SAP request has multiple behavioral modes without one versioned contract | Open | Slice 2: SAP request contract | Architecture | Critical | P0 | Structure-only and business-impact behavior span form state, API client, page orchestration, backend job outputs, and independent polling consumers. | Create StartSapJobRequest v1 with explicit mode, material, plant/context, requested artifacts, and client contract version. | Versioning adds ceremony; makes behavior reproducible and backward-compatible. | SAPForm.tsx; lib/api.ts; page.tsx; pipeline endpoints. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-022 | SAP job output lacks a unified artifact manifest | Open | Slice 2: SAP request contract | Architecture | Critical | P0 | BOM structure and business impact are retrieved separately and may finish differently without one terminal statement of what is available. | Return SapJobManifest containing job status, structure artifact, impact artifact, warnings, source context, timestamps, schema versions, and failure codes. | Requires backend change; eliminates divergent frontend polling interpretation. | /pipeline/bom/{jobId}; /pipeline/sap-impact/{jobId}. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-023 | SAP polling treats broad failures as retryable | Open | Slice 2: SAP request contract | Reliability | High | P0 | Business-impact logic retries caught errors up to the attempt limit, including failures that may be validation, authorization, or configuration errors. | Retry only defined pending/transient codes, honor Retry-After, use exponential backoff with jitter, and stop on permanent errors. | Slightly slower recovery under some transient conditions; much lower load and clearer terminal behavior. | SapBusinessImpactPanel polling loop. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-024 | Long polling has no shared cancellation chain | Open | Slice 2: SAP request contract | Reliability | High | P0 | UI cancellation/unmount, Next.js request timeout, .NET cancellation, and subprocess termination are not proven to propagate together. | Carry CancellationToken/job cancellation through every layer and kill the entire process tree. Make cleanup idempotent. | Platform-wide implementation work; prevents orphan workers and stale runtime files. | SubprocessExecutor; pipeline jobs; UI polling. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-025 | Job state is in-memory | Open | Slice 2: SAP request contract | Architecture | Critical | P0 | A service restart can lose SAP job state while connectors continue or artifacts remain on disk. | Persist job metadata and terminal states in SQL or another durable store; keep artifacts in configured object/application storage. | Adds infrastructure; required for reliable pilot use and restart recovery. | Orchestration.API/Services/JobStore.cs. | Do now | XL | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-026 | SAP runtime paths are repository-relative | Open | Slice 2: SAP request contract | Code Quality | High | P0 | Job artifacts under the source tree couple deployment, cleanup, source control, and sensitive output. | Use an injected runtime root outside the repository, validated at startup, with retention and permissions. | Requires environment configuration; fixes portability and governance. | SAP-BOM-Extractor/runtime/jobs. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-027 | Request idempotency is absent | Open | Slice 2: SAP request contract | Reliability | High | P1 | Duplicate button activation, browser retry, or network ambiguity can start duplicate SAP extraction jobs. | Accept an idempotency key derived from actor, normalized request, and client request ID. Return the existing job when safe. | Requires server record lookup; protects licensed/constrained SAP connections. | SAPForm submission and pipeline start. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-028 | No per-source concurrency or circuit breaker | Open | Slice 2: SAP request contract | Reliability | Critical | P0 | Concurrent users can exhaust SAP sessions and repeated failures can amplify an upstream outage. | Implement per-source concurrency limits, queue depth, retry budget, circuit breaker, and readiness status. | Users may queue instead of running immediately; prevents systemic source impact. | Pipeline orchestration; no breaker evidence. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-029 | SAP context is incomplete for reproducibility | Open | Slice 2: SAP request contract | Architecture | Critical | P0 | Material ID alone is insufficient when plant, valuation area, language, date, units, or organizational scope affect results. | Store all effective request context and source-system defaults in the job manifest and snapshot. Never rely on hidden backend defaults. | Makes requests more verbose; allows trustworthy replay and comparison. | SAPForm and business-impact response. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-030 | SAP API contract is not schema-validated at both boundaries | Open | Slice 2: SAP request contract | Tests | Critical | P0 | TypeScript types do not protect runtime payloads from connector/backend schema drift. | Validate request and response with versioned schemas at Next.js and .NET boundaries; reject unsupported versions explicitly. | Runtime validation has a small cost; prevents silent data loss. | lib/api.ts and dynamic payload handling. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-031 | Polling and SSE responsibilities overlap | Open | Slice 2: SAP request contract | Architecture | High | P1 | Progress may be streamed via SSE while artifacts are independently polled, creating duplicated status logic and race conditions. | Use SSE for job/manifest events with reconnect support; use artifact GET only for available artifacts. Keep one authoritative job state. | Requires event contract changes; simplifies client lifecycle. | Pipeline progress stream plus BOM/impact polling. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-032 | SAP job state machine is implicit | Open | Slice 2: SAP request contract | Code Quality | High | P0 | Queued, running, completed, failed, partial, timed out, and cancelled behavior is spread across status codes and local flags. | Define and test a state machine with valid transitions and terminal states. Reject illegal transitions and record transition timestamps. | Adds explicit model; removes impossible and stuck states. | JobStore, PipelineOrchestrator, frontend polling. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-033 | SAP pipeline lacks restart/recovery tests | Open | Slice 2: SAP request contract | Tests | Critical | P0 | There is no evidence of tests for API restart during extraction, artifact written before job update, worker crash, or duplicate completion. | Add integration tests with fake worker and durable test store for restart, orphan detection, duplicate events, cancellation, and cleanup. | Requires test harness; necessary for operational reliability. | Minimal backend tests. | Do now | XL | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-034 | Timeout values are scattered and policy-free | Open | Slice 2: SAP request contract | Code Quality | Medium | P1 | Five- to ten-minute timeouts and retry counts are embedded in routes/components without a central source policy. | Create source operation policies with wall-clock deadline, idle timeout, attempt budget, and max payload. Inject by environment. | More configuration; consistent and testable behavior. | API routes and panel polling. | Do now | S | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-035 | SAP request telemetry is insufficient for SLOs | Open | Slice 2: SAP request contract | Performance | High | P0 | Logs do not provide a complete view of queue time, source time, normalization time, artifact sizes, partial rate, and timeout rate. | Emit structured metrics and traces per job phase and artifact. Define pilot SLOs and dashboards before broad use. | Adds telemetry effort; turns incidents into diagnosable signals. | AuditLogger and console logging. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-036 | SAP presentation recomputes business summaries client-side | Open | Slice 3: SAP impact workspace | Architecture | High | P0 | The UI aggregates stock, inventory value, coverage, and warnings from response objects. Different clients could compute different meanings. | Move business-semantic aggregation to a versioned backend summary, while retaining raw line items for verification. | Backend owns more logic; yields consistent semantics across UI/export/reporting. | SapBusinessImpactPanel.tsx summary useMemo/reductions. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-037 | Mixed-currency aggregation can produce invalid totals | Open | Slice 3: SAP impact workspace | Reliability | Critical | P0 | Inventory values may be reduced and formatted using one selected/fallback currency despite heterogeneous currency contexts. | Group by currency and valuation area. Convert only with an explicit dated rate and show conversion provenance. | May remove a convenient single KPI; prevents financially misleading output. | SapBusinessImpactPanel currency selection and total reduction. | Do now | S | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-038 | Quantity and unit semantics are untyped | Open | Slice 3: SAP impact workspace | Architecture | High | P0 | Stock and inventory values can arrive as numbers/strings without one decimal precision and UOM contract. | Use decimal string or decimal type in backend, explicit UOM, source precision, and conversion status. Never use binary floating point for money. | Requires serialization rules; prevents rounding and comparison errors. | SAP response types and formatting. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-039 | Missing data and zero values risk conflation | Open | Slice 3: SAP impact workspace | Reliability | High | P0 | Blank, null, missing, unavailable, and zero are materially different for stock and valuation but can collapse during fallback formatting. | Represent availability separately from value. Test zero stock, zero price, missing valuation, unauthorized field, and not-applicable values. | More verbose model; correct business interpretation. | SapBusinessImpactPanel field helpers. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-040 | Material selection does not scale | Open | Slice 3: SAP impact workspace | Performance | High | P1 | A horizontal material-card list is rendered for all materials and can become expensive and difficult to navigate. | Virtualize a searchable material table and render details only for the selected row. | Less card-centric presentation; scales to larger responses. | SapBusinessImpactPanel material carousel. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-041 | Large location datasets are rendered eagerly | Open | Slice 3: SAP impact workspace | Performance | High | P1 | Storage locations and valuation rows can produce large DOM trees inside an already complex source panel. | Paginate or virtualize locations, with server-side paging for very large artifacts. | Adds pagination interactions; prevents browser stalls. | SapBusinessImpactPanel location tables/cards. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-042 | Business-impact artifact has no schema version displayed or enforced | Open | Slice 3: SAP impact workspace | Architecture | High | P0 | Frontend interpretation depends on the current response shape without explicit compatibility handling. | Include schemaVersion and generatedAt in every artifact; route to a version-specific adapter or fail safely. | Maintains adapters during migrations; removes silent drift. | SAP impact types/API. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-043 | Partial-data coverage is calculated inconsistently | Open | Slice 3: SAP impact workspace | Reliability | High | P1 | Coverage percentages and warning counts may be inferred locally from fields rather than declared artifact completeness. | Backend should produce completeness by domain: stock, valuation, cost, location, context, plus source warnings. | Backend complexity increases; UI becomes honest and deterministic. | SapBusinessImpactPanel coverage and warnings. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-044 | Exports can diverge from visible calculations | Open | Slice 3: SAP impact workspace | Tests | High | P1 | Client-side export may serialize raw or transformed data that does not exactly match displayed summaries. | Generate versioned exports from the same backend summary/line-item contract and add golden snapshot tests. | Requires export endpoint or shared pure formatter; improves auditability. | Client export patterns and SAP summaries. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-045 | SAP UI has no property-based boundary tests | Open | Slice 3: SAP impact workspace | Tests | High | P0 | Combinatorial payload conditions include missing arrays, duplicate materials, huge values, negative adjustments, multiple currencies, and partial domains. | Add property-based tests for parsing/aggregation invariants plus table-driven fixtures for business cases. | More sophisticated tests; high payoff for messy enterprise data. | No frontend tests visible. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-046 | Rendering logic and domain logic are interleaved | Open | Slice 3: SAP impact workspace | Code Quality | High | P0 | A large panel performs parsing, selection, aggregation, formatting, warning humanization, polling, and rendering. | Split into pure domain adapter, selector hooks, polling controller, and presentational sections. Keep domain functions framework-free. | Several small files; much easier unit testing and reuse. | SapBusinessImpactPanel.tsx. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-047 | Unknown SAP fields are silently ignored | Open | Slice 3: SAP impact workspace | Reliability | Medium | P1 | Schema additions or misspellings can disappear without diagnostics. | In development/test, report unknown fields and schema mismatch; in production, preserve raw artifact reference and log compatibility warnings. | May create noisy diagnostics during evolution; surfaces drift early. | Dynamic response interpretation. | Do now | S | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-048 | SAP impact lacks performance budgets | Open | Slice 3: SAP impact workspace | Performance | High | P1 | No limits are defined for materials, plants, locations, payload bytes, parse time, or render time. | Define tested budgets and fallback behavior, including summary-only mode and on-demand detail. | Requires product limits; prevents unbounded browser behavior. | Panel rendering and route buffers. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-049 | SAP presentation tests need domain-owner fixtures | Open | Slice 3: SAP impact workspace | Tests | Critical | P0 | Synthetic developer fixtures alone may encode incorrect SAP valuation and inventory assumptions. | Create sanitized fixtures reviewed by an SAP domain owner, with expected totals, currencies, coverage, and warnings. | Requires domain collaboration; prevents confidently wrong output. | SAP impact business semantics. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-050 | Accessibility behavior is not component-tested | Open | Slice 3: SAP impact workspace | Tests | High | P1 | Material navigation, loading, warnings, tables, and expandable sections lack keyboard and screen-reader verification. | Add component tests for tab order, row selection, status announcements, table semantics, and partial warning focus. | Test setup effort; required for enterprise usability. | SapBusinessImpactPanel. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-051 | Visualization changes share mutable normalized data assumptions | Open | Slice 4: Visualization | Architecture | High | P0 | Tree, 2D, and 3D consume related node structures but may add derived layout, selection, and analysis metadata differently. | Keep canonical input immutable. Build view-specific derived models with stable node/occurrence IDs and memoized selectors. | Additional mapping layer; prevents one view from corrupting another. | BomConstellationView; BomThreeUniverseView; visualization libs. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-052 | 2D and 3D duplicate interaction state | Open | Slice 4: Visualization | Code Quality | High | P0 | Search, difference navigation, selected node, lens, findings, requirements, breadcrumbs, and inspector behavior are implemented separately. | Create a shared VisualizationSession reducer for semantic state; keep camera/layout state view-specific. | Requires careful extraction; reduces behavioral drift without forcing one rendering abstraction. | BomConstellationView.tsx and BomThreeUniverseView.tsx. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-053 | Do not over-abstract rendering engines | Open | Slice 4: Visualization | Architecture | Medium | P1 | A single universal renderer abstraction could hide fundamental differences between SVG/DOM 2D and WebGL 3D. | Share semantic state, selectors, commands, and evidence contracts, but keep renderer implementations separate. | Some duplication remains intentionally; avoids a leaky mega-abstraction. | 2D and 3D component architecture. | Retain | S | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-054 | Layout computation can block the main thread | Open | Slice 4: Visualization | Performance | Critical | P0 | Large graph layout and analysis are computed client-side and can freeze interaction. | Move heavy layout/analysis to Web Workers with cancellation and progressive results. For production-scale snapshots, consider server precomputation. | Adds worker messaging and serialization; preserves UI responsiveness. | visualization-layout.ts; visualization-analysis.ts; large graph views. | Do now | XL | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-055 | No hard node/edge budgets | Open | Slice 4: Visualization | Performance | Critical | P0 | Adaptive behavior exists, but no enforceable maximum or fallback is visible for very large BOMs. | Define budgets per Tree/2D/3D and switch to summary/LOD modes before exceeding them. Reject or paginate unbounded payloads. | Some users lose all-nodes-at-once rendering; platform remains usable. | Constellation and 3D views. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-056 | Recursive traversal risks stack and cycle failures | Open | Slice 4: Visualization | Reliability | High | P0 | Tree transforms and graph flattening assume acyclic, reasonable-depth structures. | Use iterative traversal with occurrence-key visited tracking, explicit cycle-reference nodes, depth limit, and node budget. | More code than recursion; robust against malformed enterprise structures. | Source transforms and visualization flattening. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-057 | Node identity is not guaranteed stable across views | Open | Slice 4: Visualization | Architecture | Critical | P0 | Item IDs can repeat by occurrence and names can collide. Selection, comparison, saved views, and breadcrumbs require stable occurrence identity. | Define occurrenceId from snapshot ID plus relationship/path identity; retain part master ID separately. | Requires model migration; fixes cross-view correctness. | TreeNodeData IDs and comparison/visualization matching. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-058 | Saved views are not schema- or snapshot-versioned | Open | Slice 4: Visualization | Reliability | High | P1 | Local saved Constellation views can reference stale nodes or incompatible lens/layout fields. | Persist snapshot ID, view schema version, and compatibility check. Reject or migrate invalid views. | Old local views may be discarded; avoids incorrect restoration. | BomConstellationView localStorage. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-059 | WebGL resource disposal is not proven | Open | Slice 4: Visualization | Performance | High | P0 | Repeated switching/fullscreen/unmount can leak geometries, materials, textures, controls, or animation frames. | Audit and test disposal on unmount and data replacement; reuse geometries/materials where safe. | Adds renderer-specific tests and instrumentation; prevents session degradation. | BomThreeUniverseView and Three.js resources. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-060 | 3D error boundary lacks telemetry and fallback state | Open | Slice 4: Visualization | Reliability | High | P0 | The boundary catches render failures but does not record GPU/browser context, correlation, or preserve selection in a fallback. | Emit sanitized render telemetry and transition to 2D/Tree with selection and lens state preserved. | Telemetry needs privacy review; provides actionable recovery. | BomThreeUniverseView Boundary. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-061 | Graph search can be O(n) repeatedly | Open | Slice 4: Visualization | Performance | High | P1 | Search, corresponding-part lookup, findings, and breadcrumb resolution can repeatedly walk full node collections. | Build memoized indexes by occurrence ID, normalized item ID, name token, comparison status, and parent. | Uses memory proportional to nodes; materially improves repeated interactions. | Visualization search/navigation logic. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-062 | Minimap and overlay calculations trigger frequent React work | Open | Slice 4: Visualization | Performance | Medium | P1 | Pointer/camera/transform changes can cause repeated state updates and overlay rerenders. | Keep high-frequency transform state outside React or throttle with requestAnimationFrame; publish only semantic changes. | More imperative renderer code; smoother interaction. | Constellation minimap/transform and 3D camera state. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-063 | Visualization analysis has no deterministic benchmark corpus | Open | Slice 4: Visualization | Tests | Critical | P0 | Findings, centrality, risk, change severity, and lens behavior cannot be safely optimized without expected outputs. | Create golden graph fixtures with exact expected metrics/findings and tolerance rules. | Requires fixture design; enables confident performance refactoring. | visualization-analysis.ts. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-064 | No scale test matrix | Open | Slice 4: Visualization | Tests | Critical | P0 | There is no automated evidence for 1k, 10k, 50k, or pathological deep/wide/cyclic BOMs. | Add synthetic scale fixtures and measure normalization, layout, render readiness, interaction latency, memory, and cleanup. | CI time may increase; run smoke budgets per PR and full matrix nightly. | No visualization performance suite visible. | Do now | XL | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-065 | Comparison and visualization status precedence is implicit | Open | Slice 4: Visualization | Code Quality | High | P1 | A node may simultaneously be selected, changed, probable, requirement-linked, impacted, and Windchill-highlighted. Each view can resolve styles differently. | Create a pure evidence-priority function and shared legend contract, with exhaustive combination tests. | May simplify some decorative combinations; guarantees semantic consistency. | TreeRow, Constellation, 3D node styling. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-066 | Animation lifecycle is not covered by reduced-motion tests | Open | Slice 4: Visualization | Tests | Medium | P1 | Tours, pulses, camera movement, and transitions can continue conceptually even when CSS duration is reduced. | Make motion policy a dependency and test instant/no-pulse behavior under reduced motion. | Adds conditional paths; improves accessibility and deterministic tests. | Visualization tours, Node3 pulse, camera rig. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-067 | Export size and memory usage are unbounded | Open | Slice 4: Visualization | Performance | High | P1 | PNG/SVG export of large graphs can allocate very large canvases/strings and block the browser. | Enforce export dimensions/node limits, estimate size before export, and use server-side export for large snapshots. | Large exports require a different workflow; avoids browser crashes. | Constellation export PNG/SVG. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-068 | Visualization commands lack undo/restore boundaries | Open | Slice 4: Visualization | Reliability | Medium | P2 | Pinning, isolation, hiding, lens changes, and saved views may leave users in complex state without deterministic reset. | Define session reset, command history limits, and serialization tests. Keep destructive state view-local. | Adds state-machine discipline; improves recoverability. | Constellation interaction tools. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-069 | Renderer dependency upgrades are ungoverned | Open | Slice 4: Visualization | Code Quality | Medium | P2 | Three.js/d3/renderer versions can alter layout, GPU behavior, or output without visual/benchmark gates. | Pin versions, use lockfile CI, review release notes, and require visual/performance regression checks for upgrades. | Slower dependency upgrades; lower surprise risk. | Frontend package dependencies and visualization stack. | Do now | S | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-070 | Visualization code lacks component ownership boundaries | Open | Slice 4: Visualization | Code Quality | High | P1 | Large view components and many tool panels make it unclear which module owns semantic state, rendering, analysis, or overlays. | Document ownership and module layering: domain selectors, session reducer, layout worker, renderer, inspector, overlay shell, exports. | Documentation and refactor cost; enables parallel development without collisions. | Visualization component structure. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-071 | Connector utility discovery is duplicated across routes | Open | Cross-cutting | Code Quality | High | P1 | fileExists, Python discovery, candidate script paths, and execution setup are repeated in multiple Next.js routes. | Create one ConnectorProcessRunner with injected locator, timeout policy, redaction, cancellation, and result envelope. | Centralizes sensitive execution code; avoid making it a generic framework beyond current connector needs. | bom-configit and bom-windchill routes; repeated helpers. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-072 | Subprocess execution remains inside the web tier | Open | Cross-cutting | Architecture | Critical | P0 | Next.js routes execute Python connector processes directly, coupling web request lifetime, filesystem layout, secrets, and worker load. | Move execution behind the .NET orchestration job boundary. Keep Next.js as BFF/UI. | Migration work and temporary compatibility route; substantially safer production topology. | Frontend API routes and .NET orchestration. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-073 | Catch-all exception handling conceals partial data loss | Open | Cross-cutting | Reliability | Critical | P0 | Backend integration sources contain many broad catches, including ignored exceptions around source-property extraction. | Replace ignored catches with typed optional-field outcomes or logged partial warnings. Fail required-field operations explicitly. | More warning handling and tests; prevents silently incomplete BOMs. | Bundle scan: extensive catch(Exception) patterns in integration code. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-074 | Reflection is repeated in Teamcenter variant extraction | Open | Cross-cutting | Performance | High | P1 | SDK compatibility reflection can occur repeatedly per property/rule and exceptions are used as flow control. | Resolve supported methods once per SDK/runtime, cache delegates, and expose capability flags. | Adds a compatibility adapter; reduces repeated overhead and noisy catches. | Teamcenter variant extraction methods. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-075 | Recursive connector traversal is chatty | Open | Cross-cutting | Performance | High | P1 | Repeated getProperties calls and recursive traversal can create excessive Teamcenter round trips. | Batch property requests by level/batch, memoize loaded objects, and measure source-call counts. | More complex batching; major latency and source-load reduction. | Teamcenter extractor traversal. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-076 | Custom serialization increases compatibility risk | Open | Cross-cutting | Code Quality | Medium | P1 | Some integration code manually constructs JSON and supports multiple child array shapes. | Use one mature serializer with explicit DTOs, schema version, null policy, and golden examples. | DTO maintenance; removes escaping and drift risks. | Teamcenter/Configit integration source. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-077 | No complete CI quality gate | Open | Cross-cutting | Tests | Critical | P0 | The repository lacks demonstrated gates for frontend tests, backend tests, contract tests, lint, typecheck, security, and artifact hygiene. | Create CI stages: hygiene, build/typecheck, unit, contract, integration, visual/accessibility, performance smoke, package. | Longer CI; parallelize fast gates and schedule expensive matrices. | Sparse tests and mixed generated artifacts. | Do now | XL | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-078 | No deployment artifact and rollback verification | Open | Cross-cutting | Reliability | High | P0 | The engineering plan does not prove immutable frontend/backend builds, environment validation, health checks, or rollback for these changes. | Build immutable artifacts, validate configuration at startup, canary the four flags, and automate rollback on health/SLO failure. | Deployment pipeline work; makes branch separation operationally useful. | PM2/internal deployment context; no release pipeline evidence. | Do now | L | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-079 | No ownership/RACI for multi-runtime failures | Open | Cross-cutting | Architecture | High | P1 | Incidents can span browser, Next.js, .NET, Python/Java, SAP, Teamcenter, Windchill, or Configit without clear service ownership. | Assign owner and escalation path per connector and platform service; include on-call runbooks and dashboards. | Organizational work; reduces multi-team incident delay. | Multi-runtime architecture. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.
ENG-080 | Engineering success criteria are not measurable | Open | Cross-cutting | Performance | High | P0 | The branch can be declared done based on functionality without latency, correctness, reliability, or regression thresholds. | Adopt explicit gates: contract pass rate, comparison correctness, job completion/partial rates, p95 timings, memory budgets, accessibility, and zero critical regressions. | Requires baseline measurement; prevents subjective readiness claims. | Current diff and absent performance/test certification. | Do now | M | TBD |  | Implementation is covered by deterministic tests, explicit failure handling, telemetry, and a documented rollback path.