## Issue Register
ID | Title | Status | Category | Severity | Priority | Description | Recommended_Solution | Evidence | Review_Phase | Effort | Owner | Dependencies | Decision
CEO-001 | No verified authentication or authorization boundary | Open | Security | Critical | P0 | The orchestration API and connector routes expose enterprise extraction and product data operations without visible user identity, role checks, or source-level entitlements. | Make enterprise SSO and server-side authorization a production gate. Define roles, source entitlements, product-level access checks, and denied-access audit events before wider rollout. | Orchestration.API/Program.cs; frontend/app/api/bom-*.ts; no auth middleware or endpoint attributes found. | Production gate | XL | TBD |  | Required
CEO-002 | Development CORS policy is unrestricted | Open | Security | Critical | P0 | The API uses AllowAnyOrigin, AllowAnyMethod and AllowAnyHeader. In a reachable environment this weakens the browser trust boundary. | Replace with environment-specific allowlists, explicit methods and headers, credential policy, and automated configuration tests. Fail startup if production uses the development policy. | OrchestrationPlatform/Orchestration.API/Program.cs: AllowAnyOrigin/Method/Header. | Production gate | S | TBD |  | Required
CEO-003 | Configit credential handling is unsafe by design | Open | Security | Critical | P0 | Repository documentation says the Configit base URL, API key and SSL verification setting are embedded in config.py. This creates secret exposure and rotation risk. | Remove embedded credentials, rotate any exposed key, use a secret vault or protected environment injection, and scan Git history. Never expose debug raw responses to untrusted callers. | configit_extractor/README.md; references to embedded API key and config.py. | Production gate | M | TBD |  | Required
CEO-004 | Connector subprocesses execute inside web request paths | Open | Architecture | High | P0 | Next.js API routes locate Python and run extractors directly. Long-running connector work is coupled to web process lifetime, filesystem layout, and request timeout. | Move connector execution behind the orchestration service and durable job queue. Keep Next.js as BFF/UI only. Use versioned job APIs and event streaming. | frontend/app/api/bom-configit/route.ts; frontend/app/api/bom-windchill/route.ts. | Architecture foundation | L | TBD |  | Required
CEO-005 | Jobs are in-memory and disappear on restart | Open | Reliability | Critical | P0 | Job state is held by an in-memory JobStore. Restarting the API can orphan running work and erase diagnostic state. | Persist job metadata and terminal outcomes in SQL; store payloads in a versioned snapshot/object store. Rehydrate active jobs after restart and mark unknown workers explicitly. | Orchestration.API/Services/JobStore.cs; Program.cs service registration. | Architecture foundation | L | TBD |  | Required
CEO-006 | Runtime output is written inside the repository | Open | Operations | High | P0 | SAP job directories and extractor outputs accumulate under source folders, mixing runtime data, product IP and code. | Move runtime data to configured application-data/object-storage locations outside the repo. Add retention, cleanup, access controls, encryption and startup validation. | SAP-BOM-Extractor/runtime/jobs; untracked job_* folders in audit. | Stabilization | M | TBD |  | Required
CEO-007 | Runtime outputs and test fixtures are not clearly separated | Open | Data governance | High | P0 | Extraction JSON files are repeatedly modified or deleted while also serving as samples or current output. This makes demos, tests and operations ambiguous. | Create immutable sanitized fixtures under fixtures/contracts and fixtures/edge-cases. Ignore runtime/latest outputs and identify every committed data file by purpose and classification. | tc_extraction.json deletions; windchill_extraction.json, configit_extraction.json and sap_bom_extraction.json history. | Stabilization | M | TBD |  | Required
CEO-008 | Teamcenter polling can continue for about 50 minutes | Open | Reliability | High | P0 | Legacy BOM streaming allows 2,000 attempts at 1.5 seconds each. This masks stuck jobs, creates network load and gives users no bounded terminal outcome. | Replace with durable job status plus SSE reconnection, maximum wall-clock deadline, cancellation and explicit TIMED_OUT/WORKER_LOST states. | frontend/components/BomStreamViewer.tsx: TEAMCENTER_MAX_FETCH_ATTEMPTS=2000 and 1500 ms delay. | Stabilization | M | TBD |  | Required
CEO-009 | SourceBomPanel is a platform-level responsibility hotspot | Open | Architecture | High | P0 | One component owns fetching, polling, transformation lifecycle, tree, 2D, 3D, fullscreen, comparison, impact, requirements and global overlays. It is the most frequently touched meaningful file. | Keep the visual shell but separate SourceRuntimeController, BomWorkspaceState, VisualizationHost and page-level GlobalOverlayHost. Decompose by ownership, not by arbitrary file size. | frontend/components/SourceBomPanel.tsx; 12 touches in 30-day audit. | Architecture foundation | L | TBD |  | Required
CEO-010 | Workspace page is a growing source-specific state machine | Open | Architecture | High | P0 | The comparison page holds independent state branches and request flows for Teamcenter, SAP, Configit, Windchill, Excel, revisions, change impact and comparison. | Introduce a typed source-adapter registry and reducer/state machine. Each adapter defines form, start/load behavior, capabilities and cleanup while common workspace lifecycle remains centralized. | frontend/app/bom-comparison/page.tsx; 11 touches and many source-specific states/branches. | Architecture foundation | L | TBD |  | Required
CEO-011 | BOM transformation logic is duplicated | Open | Maintainability | High | P0 | Teamcenter, Configit and related transforms exist in multiple viewers and page-level code, with differing payload assumptions and identity behavior. | Create one pure adapter per source with schema validation, canonical mapping and versioned fixtures. Delete or archive obsolete viewers only after usage verification. | BomViewer.tsx; BomStreamViewer.tsx; page.tsx SAP transform; source adapter logic. | Architecture foundation | M | TBD |  | Required
CEO-012 | Canonical BOM model is too weak for enterprise comparison | Open | Data architecture | Critical | P0 | TreeNodeData mixes identity and attributes in free-form maps. It does not reliably distinguish part master, occurrence, relationship, source revision, effectivity, units or provenance. | Define CanonicalBomSnapshot, PartIdentity, OccurrenceIdentity and BomRelationship contracts. Preserve raw source payload reference and transformation version. Provide compatibility projection to TreeNodeData during migration. | types/bom-comparison.ts; transforms use Record<string, scalar> attributes. | Architecture foundation | XL | TBD |  | Required
CEO-013 | Cross-system identity is heuristic but appears authoritative | Open | Product trust | Critical | P0 | Comparison and impact rely on item IDs and normalized names. Users may interpret probable matches and corresponding parts as confirmed digital-thread links. | Create an identity confidence model with fact/rule/suggestion labels. Persist approved cross-references, show alternatives, and prevent heuristic matches from silently becoming authoritative. | lib/bom-comparison.ts; cross-bom-impact and requirement matching flows. | Core intelligence | L | TBD |  | Required
CEO-014 | Comparison uses greedy matching rather than global assignment | Open | Core intelligence | High | P1 | Pairwise candidate consumption can produce locally plausible but globally inferior cross-source matches, especially with repeated names and occurrences. | Benchmark deterministic bipartite/global assignment for ambiguous candidate groups. Retain exact IDs first, then solve constrained candidate sets and expose why a candidate won. | frontend/lib/bom-comparison.ts matching sequence and used-candidate behavior. | Core intelligence | L | TBD |  | Required
CEO-015 | Comparison thresholds are not calibrated by source pair | Open | Core intelligence | High | P1 | A fixed heuristic threshold is applied across PLM, CPQ, ERP and Excel despite different naming, hierarchy and revision semantics. | Build versioned benchmark fixtures per source pair, measure precision/recall, and configure policies by Teamcenter-SAP, Windchill-SAP, PLM-Configit, Excel-source, etc. | frontend/lib/bom-comparison.ts score threshold and weights. | Core intelligence | M | TBD |  | Required
CEO-016 | Quantity and unit semantics are not normalized | Open | Data quality | High | P0 | Sources represent quantity and unit in different formats. String comparison can create false differences or miss meaningful ones. | Use decimal quantity plus explicit UOM, source value, conversion status and precision. Compare only when units are compatible and explain skipped comparisons. | Source transforms; comparison type fields; Configit quantity rendered as string. | Architecture foundation | M | TBD |  | Required
CEO-017 | Revision, configuration and effectivity context are not first-class | Open | Data architecture | Critical | P0 | A BOM without revision rule, view, plant, date, variant selections and effectivity is not reproducibly comparable. | Require SnapshotContext on every extraction. Show it in workspace and exports; block or warn when comparing incompatible contexts. | Connector inputs and TreeNodeData omit consistent extraction context. | Architecture foundation | L | TBD |  | Required
CEO-018 | No durable BOM snapshot or reproducible session | Open | Product | High | P0 | Loaded roots and comparison sessions vanish on refresh, making results non-reproducible and preventing audit, sharing and later review. | Persist immutable snapshots and saved workspaces with extraction timestamp, connector version, context and user. Use URLs that reference saved sessions without exposing identifiers directly. | Frontend module/local state; no demonstrated snapshot persistence. | Platform productization | XL | TBD |  | Required
CEO-019 | Requirement traceability is demo data but can look live | Open | Product trust | Critical | P0 | Requirement history is loaded from local structured data while UI presents rich traceability semantics. Stakeholders may infer authoritative ALM connectivity. | Add a persistent DEMO DATA badge and provenance panel now. Later implement a permission-aware Codebeamer connector with explicit trace links and timestamps. | frontend/data/hardcoded-part-requirements.json; requirement trace store and drawer. | Stabilization | S | TBD |  | Required
CEO-020 | Global overlay ownership is implemented through a singleton workaround | Open | Architecture | High | P0 | RequirementsExplorerModal is instantiated by repeated source panels and suppresses duplicates using a module-level activeOwner symbol. | Mount one GlobalOverlayHost at workspace page level. Overlays subscribe to central workspace state and never depend on which source panel mounted first. | RequirementsExplorerModal.tsx activeOwner; RequirementTraceWorkspace.tsx intentionally empty; SourceBomPanel.tsx overlayOwner. | Architecture foundation | M | TBD |  | Required
CEO-021 | Multiple legacy BOM viewer implementations remain active in source | Open | Maintainability | Medium | P1 | BomViewer, BomStreamViewer and SourceBomPanel overlap. Legacy polling and transform code can be accidentally reused or misread as current truth. | Run import/reference analysis, designate SourceBomPanel architecture as current, migrate reusable pure transforms, then delete or archive dead viewers with a regression build. | frontend/components/BomViewer.tsx; BomStreamViewer.tsx; SourceBomPanel.tsx. | Stabilization | S | TBD |  | Required
CEO-022 | Dropped Radial Explorer remains in code and host logic | Open | Product coherence | Medium | P1 | The product direction dropped the standalone radial view, but component, layout types and SourceBomPanel branch remain. | Verify no user route depends on it, remove component/import/types/tests, and update documentation. Keep radial-clusters only as a Constellation layout term. | BomRadialExplorerView.tsx; SourceBomPanel.tsx radial branch; master documentation drift. | Stabilization | S | TBD |  | Required
CEO-023 | Product promise exceeds implemented connector reality | Open | Strategy | High | P0 | Homepage and source picker mention Codebeamer, Oracle and Servigistics even though active source definitions support Teamcenter, Windchill, SAP, Configit and Excel. | Separate Available now, Pilot, and Roadmap. Do not present non-working systems as equivalent capabilities. Use capability flags backed by health/configuration. | frontend/app/page.tsx capability badges; QuickStartModal categories versus defs. | Stabilization | S | TBD |  | Required
CEO-024 | The platform lacks a single primary user and hero workflow | Open | Strategy | High | P0 | The platform serves extraction, comparison, impact, requirements, change review, SAP analysis, Excel import and visualization equally. This risks perceived feature collection rather than a must-have product. | Position the hero workflow as Engineering Change and Discrepancy Review: load/resolve context, explain changes, quantify exposure, review evidence, produce actions. Other pillars are supporting capabilities. | Current pillar breadth and workspace navigation. | CEO decision | M | TBD |  | Required
CEO-025 | Source-centric information architecture obscures task outcomes | Open | Strategy | High | P1 | The workspace is organized around source cards and technical systems rather than user jobs such as review change, reconcile BOMs or investigate exposure. | Retain source onboarding but add task entry points and saved review workspaces. Sources become evidence providers inside a review, not the top-level product purpose. | frontend/app/bom-comparison/page.tsx groups by PLM/ERP/CPQ/DATA. | Platform productization | L | TBD |  | Required
CEO-026 | Client-side comparison can freeze and exposes full datasets | Open | Performance/Security | High | P0 | All loaded source structures are delivered to the browser and compared synchronously. Large BOMs risk UI stalls and unnecessary data exposure. | Introduce a worker boundary immediately for UI safety, then server-side comparison over authorized snapshots for production. Return paged summaries and on-demand branches. | page.tsx compareMultipleBoms useMemo; client-side lib/bom-comparison.ts. | Scale foundation | L | TBD |  | Required
CEO-027 | Graph views lack enforceable operating limits | Open | Performance | High | P1 | 2D and 3D include adaptive rendering, but there is no clear hard budget, fallback policy or server-side pagination for very large BOMs. | Define tested node/edge budgets. Auto-select Tree/summary mode beyond thresholds, provide sampled/LOD graph, and keep highlighted evidence at full fidelity. | BomConstellationView.tsx; BomThreeUniverseView.tsx; no enforced max structures. | Scale foundation | L | TBD |  | Required
CEO-028 | 3D error boundary provides no actionable recovery | Open | Reliability | Medium | P1 | The WebGL boundary displays only “3D rendering unavailable,” without reason, telemetry, fallback action or correlation details. | Capture render errors, log browser/GPU capability safely, provide Return to Tree and Retry 3D actions, and track 3D failure rate. | BomThreeUniverseView.tsx Boundary class. | Stabilization | S | TBD |  | Required
CEO-029 | Observability is logs, not an operational system | Open | Operations | Critical | P0 | The platform lacks demonstrated metrics, traces, dashboards, alerts and correlation across browser, Next.js, .NET, Java/Python and source systems. | Adopt OpenTelemetry correlation. Define source extraction SLIs, job age, failure codes, queue depth, payload size, normalization errors, comparison latency and client render failures. Provide dashboard, alerts and runbooks. | File-based AuditLogger and console logging; no metrics/tracing evidence. | Production gate | XL | TBD |  | Required
CEO-030 | Errors are still mapped from free-form strings | Open | Reliability | High | P0 | User-facing error improvements categorize outcomes by message and status, but connector/backend contracts do not consistently emit stable error codes. | Define versioned ErrorEnvelope with code, category, safeMessage, retryable, correlationId and technicalReference. Map source-native errors once at connector boundary. | frontend/lib/user-facing-errors.ts; route handlers return error strings. | Stabilization | M | TBD |  | Required
CEO-031 | Catch-all exception suppression risks silent data loss | Open | Reliability | Critical | P0 | Backend sample/integration code contains many catch(Exception) patterns, including ignored exceptions, which can hide partial extraction or variant-rule failures. | Eliminate empty catches. Name connector exceptions, record affected object/phase, fail or mark partial results explicitly, and add tests that prove no silent omission. | Bundle count: 80 catch(Exception variants); Teamcenter/Configit integration sources. | Production gate | L | TBD |  | Required
CEO-032 | System.exit is used in integration code | Open | Reliability | High | P0 | Connector/sample code invokes System.exit, which is unsafe when reused in a managed worker or orchestration process. | Return typed exit results from connector entrypoints. Isolate any legacy executable in a worker process and interpret exit codes centrally. | TeamCenter-to-Configit source bundle contains multiple System.exit calls. | Stabilization | M | TBD |  | Required
CEO-033 | Subprocess timeout does not provide full cancellation semantics | Open | Reliability | High | P0 | Routes set execution timeouts, but platform-wide cancellation, child-process tree termination and connector cleanup are not proven. | Implement cancellation tokens from API to worker, kill process trees, mark terminal CANCELLED/TIMED_OUT state, and clean temporary/output files idempotently. | Next.js execFile timeouts; .NET SubprocessExecutor/PipelineOrchestrator. | Architecture foundation | L | TBD |  | Required
CEO-034 | No connector circuit breaker or source throttling | Open | Reliability | High | P1 | Concurrent users can overwhelm SAP sessions, Teamcenter pools or other licensed systems, and repeated failures can amplify outages. | Add per-source concurrency limits, rate limits, circuit breakers, retry budgets and health state. Expose source availability before request submission. | Connector architecture and job orchestration; no breaker/backpressure evidence. | Production gate | L | TBD |  | Required
CEO-035 | Source requests are not proven idempotent | Open | Reliability | High | P1 | Double-clicks, retries or network ambiguity may create duplicate extraction jobs and repeated source load. | Accept an idempotency key derived from actor, source, normalized request and time window. Return existing active/succeeded snapshot when policy allows. | Forms and start endpoints; no idempotency contract visible. | Architecture foundation | M | TBD |  | Required
CEO-036 | Exports are ungoverned and unaudited | Open | Security | Critical | P0 | Client-side JSON/CSV and impact exports can create unmanaged copies of sensitive product structures without permission checks, classification or audit. | Enforce export entitlement server-side, classify/watermark reports, log actor/snapshot/purpose, set payload limits, and support disabled export policy. | ComparisonSummary.tsx; ImpactAnalysisWorkspace.tsx; client Blob downloads. | Production gate | L | TBD |  | Required
CEO-037 | Raw technical details may disclose sensitive internals | Open | Security | High | P0 | TechnicalDetails can expose backend messages to users and copy them to clipboard. Route errors can include subprocess stderr and local paths. | Return safe user messages and opaque technical reference IDs. Restrict detailed diagnostics to authorized support views and scrub paths, tokens and identifiers. | TechnicalDetails.tsx; bom-windchill route stderr tail; user-facing error mapping. | Stabilization | M | TBD |  | Required
CEO-038 | Debug response can return raw Configit data and runtime paths | Open | Security | High | P0 | The Configit route supports debug=1 and returns raw response, Python executable and script path. | Remove in production or require privileged support authorization. Redact payloads and paths, and audit access. | frontend/app/api/bom-configit/route.ts debug branch. | Stabilization | S | TBD |  | Required
CEO-039 | No payload schema validation at connector boundaries | Open | Data quality | Critical | P0 | Routes and transforms inspect unknown objects dynamically. Schema drift can silently drop fields or misclassify empty results as pending. | Use versioned JSON Schema/Zod/.NET contracts at ingress and canonical output. Reject unsupported versions with SCHEMA_UNSUPPORTED and preserve validation diagnostics. | record/asRecord dynamic parsing across routes and transforms. | Architecture foundation | L | TBD |  | Required
CEO-040 | Tree transforms do not consistently protect against cycles or extreme depth | Open | Reliability | High | P1 | Recursive transforms and searches assume acyclic reasonable-depth structures. Enterprise BOMs can contain pathological references or malformed payloads. | Normalize iteratively with visited occurrence keys, maximum depth/node budgets and explicit cycle-reference nodes. Test deep, wide and cyclic fixtures. | Recursive source transforms and find functions in frontend. | Scale foundation | M | TBD |  | Required
CEO-041 | Generated build artifacts have polluted Git history | Open | Engineering hygiene | Medium | P1 | bin/obj files appear among recently touched files and stashes despite ignore rules, indicating tracked generated artifacts. | Identify tracked build outputs, remove them from index in a dedicated hygiene commit, strengthen ignore rules, and add CI check against generated artifacts. | Audit recently touched files and three stashes. | Stabilization | S | TBD |  | Required
CEO-042 | Three stashes contain mostly generated outputs | Open | Engineering hygiene | Low | P2 | Stashes 0 and 1 appear duplicated and contain only obj files; stash 2 includes obj and extraction samples. | After a no-loss review, document hashes/file lists, archive any meaningful fixture changes, then drop generated-only stashes. | git stash file lists in source bundle. | Stabilization | S | TBD |  | Required
CEO-043 | Line-ending policy is not explicit | Open | Engineering hygiene | Medium | P1 | LF-to-CRLF warnings appear for all active frontend changes, risking noisy diffs and accidental whole-file modifications. | Add .gitattributes and EditorConfig with explicit text/eol policy, renormalize in an isolated commit, and align formatters. | Git diff warnings; no root .gitattributes/.editorconfig included. | Stabilization | S | TBD |  | Required
CEO-044 | Test coverage is far below product complexity | Open | Quality | Critical | P0 | The bundle shows one meaningful AuditLogger test and a placeholder UnitTest1, with no visible frontend unit/component/E2E suite for the primary flows. | Establish a test pyramid: adapter fixtures, canonical model, comparison benchmarks, state reducers, component states, connector contract mocks, Playwright smoke, large-BOM performance and security tests. | Orchestration.API.Tests/AuditLoggerTests.cs; UnitTest1; no frontend tests found. | Production gate | XL | TBD |  | Required
CEO-045 | There is no versioned regression corpus for matching | Open | Quality | Critical | P0 | Comparison behavior cannot be safely tuned without labeled source-pair fixtures and expected matches/differences. | Create sanitized golden datasets per source pair, including duplicate IDs, moves, units, revisions, alternates, missing fields and probable matches. Track precision/recall and false-positive budget in CI. | Comparison engine present; no benchmark fixture suite demonstrated. | Core intelligence | L | TBD |  | Required
CEO-046 | No large-BOM performance certification | Open | Quality | High | P1 | The product has performance optimizations but no evidence of repeatable budgets for 1k, 10k, 100k or larger occurrence structures. | Create synthetic and sanitized scale fixtures. Measure extraction, normalization, comparison, tree interaction, 2D, 3D, memory and export. Gate releases against budgets. | Visualization performance code; no benchmark suite included. | Scale foundation | L | TBD |  | Required
CEO-047 | Accessibility is inconsistent across advanced workspaces | Open | Quality | High | P1 | Some modals implement focus behavior, while others lack focus trapping, labels or keyboard-equivalent graph navigation. 2D/3D cannot be the only way to access evidence. | Adopt WCAG-focused component primitives, run axe in CI, guarantee Tree/table fallback, provide keyboard node navigation and announce selection/status changes. | QuickStart modal has focus trap; other overlays and graph SVG/WebGL controls vary. | Product quality | L | TBD |  | Required
CEO-048 | Modal, drawer and Escape behavior have no single interaction stack | Open | Frontend architecture | High | P1 | Fullscreen, comparison modal, requirement evolution, requirements drawer, findings, context menus and other overlays independently listen for Escape and manage z-index/body overflow. | Introduce an overlay manager with stack order, focus return, scroll lock and Escape ownership. Test nested overlay plus fullscreen behavior. | Multiple components with independent key listeners and z-index values up to 10000. | Architecture foundation | M | TBD |  | Required
CEO-049 | Comparison loader simulates work with fixed timers | Open | Product trust | Medium | P1 | The transition displays staged processing and completes after 2.2 or 3 seconds rather than reflecting actual computation progress. | Either make the transition a brief honest UI transition, or bind stages to actual worker/service events. Never imply work is occurring when it completed instantly. | frontend/components/ComparisonLoader.tsx intervals and fixed timeout. | Stabilization | S | TBD |  | Required
CEO-050 | Client saved views are browser-local and ungoverned | Open | Product | Medium | P2 | Constellation saved views live in localStorage, cannot be shared, audited or tied to a snapshot, and may become invalid when a BOM changes. | Include snapshot/version in saved view identity. For pilots, label as local; for productization, persist user-owned views with migration/version validation. | BomConstellationView.tsx localStorage saved views. | Platform productization | M | TBD |  | Required
CEO-051 | SAP impact aggregation can combine mixed currencies | Open | Product trust | Critical | P0 | Summary inventory value reduces values across returned materials and formats them using a selected/fallback currency. If materials span currencies, the total is misleading. | Group totals by currency and valuation area, or convert only with explicit dated rates. Never show one money total for heterogeneous currencies. | SapBusinessImpactPanel.tsx summary.value reduction and currency selection. | Stabilization | S | TBD |  | Required
CEO-052 | SAP polling retries all failures without classifying retryability | Open | Reliability | High | P1 | Business-impact loading retries up to 45 times for any caught error, including validation or authorization failures that should terminate immediately. | Retry only 202/404-not-ready and defined transient codes with exponential backoff and jitter. Stop on validation/auth/configuration errors and honor Retry-After. | SapBusinessImpactPanel.tsx attempt loop. | Stabilization | M | TBD |  | Required
CEO-053 | SAP business impact and BOM lifecycle can diverge | Open | Product | High | P1 | BOM structure and business-impact results are loaded through separate consumers and may reach different terminal times or partial states without a single job outcome. | Model one extraction job with named artifacts and statuses: structure, material context, inventory, valuation, warnings. Display a unified result manifest. | page.tsx SourceBomPanel plus SapBusinessImpactPanel; shared jobId but independent polling. | Architecture foundation | M | TBD |  | Required
CEO-054 | Excel corrections are not persisted as governed learning | Open | Product | Medium | P1 | Users can override mappings, but approved corrections are session-local and cannot become reusable templates or audited source-specific rules. | Save mapping profiles by organization/template signature with explicit approval, versioning and rollback. Preserve workbook fingerprint and correction rationale. | ExcelBomImportWorkspace.tsx local mapping state. | Platform productization | L | TBD |  | Required
CEO-055 | Excel hierarchy auto-detection lacks explicit ambiguity gate | Open | Product trust | High | P1 | The engine can choose a hierarchy mode by score, but high-impact ambiguity should require review rather than silently loading a plausible structure. | Define confidence/margin thresholds. When top candidates are close or root/depth differs materially, require user selection and show side-by-side evidence. | Excel engine candidates and auto mode in ExcelBomImportWorkspace. | Core intelligence | M | TBD |  | Required
CEO-056 | Windchill operations are overloaded into one GET route | Open | API design | High | P1 | Extract, versions, structure, compare, change-impact and search share query-driven GET execution, including long-running and semantically complex operations. | Split read queries from asynchronous commands. Use typed endpoints, POST job creation for expensive operations, request schemas, cancellation and idempotency. | frontend/app/api/bom-windchill/route.ts Operation union and GET handler. | Architecture foundation | L | TBD |  | Required
CEO-057 | Unsafe identifiers and product data can enter URLs and logs | Open | Security | High | P1 | Part IDs, product IDs and versions are sent in query strings, which may be retained in browser history, proxies and logs. | Use POST bodies for sensitive commands, minimize logged identifiers, apply redaction/hashing policy, and keep user-facing deep links based on internal snapshot IDs. | bom-windchill and bom-configit query parameters; frontend fetch URLs. | Production gate | M | TBD |  | Required
CEO-058 | No explicit data retention, deletion or classification controls | Open | Data governance | Critical | P0 | BOMs, requirements, inventory, valuation and change data are sensitive, but no enforceable retention, classification or deletion workflow is visible. | Classify data by source, define retention and legal requirements, encrypt snapshots, support deletion, and expose lineage. Runtime and exported copies need separate policies. | Runtime jobs, local files, exports and no persistent governance layer. | Production gate | XL | TBD |  | Required
CEO-059 | No deployment safety model or feature flags is demonstrated | Open | Operations | High | P1 | The platform integrates many connectors and experimental visualization/workflow features, but partial deployment, rollback and capability gating are not evident. | Use environment-validated configuration, connector capability flags, kill switches, canary deployment, immutable artifacts and automated rollback. | PM2/frontend and .NET project evidence; no feature flag framework found. | Production gate | L | TBD |  | Required
CEO-060 | Product metrics are feature-centric rather than outcome-centric | Open | Strategy | High | P1 | Current telemetry recommendations focus on calls and durations, but the platform has no demonstrated measurement of investigation time saved, review completion or avoided errors. | Define north-star outcomes: time to trusted change assessment, discrepancy resolution rate, manual navigation avoided, approved match rate and evidence completeness. Instrument journeys, not vanity clicks. | Current platform feature catalogue and absent product analytics evidence. | CEO decision | M | TBD |  | Required
CEO-061 | No explicit support and connector ownership model | Open | Operations | High | P1 | Failures span frontend, orchestration, Java/Python runtimes and enterprise systems, but ownership and escalation boundaries are not encoded. | Define RACI per connector and service, support hours, source-system handoff, severity policy, runbooks and correlation-ID based triage. | Multi-runtime architecture; documentation lists ownership as unresolved. | Production gate | M | TBD |  | Required
CEO-062 | The current working tree mixes unrelated change themes | Open | Engineering governance | High | P0 | SAP refinement, error handling, Excel, layout and visualization performance exist together as uncommitted work. Regression attribution and review are difficult. | After validation, split by coherent change intent without losing work. Establish a clean integration branch rule and PR-level acceptance evidence. | Git status and diff stat: 20 modified frontend files plus new feedback components. | Stabilization | M | TBD |  | Required
CEO-063 | Repository documentation contains current-state contradictions | Open | Governance | Medium | P1 | The master document contains dropped Radial references and differing Next.js versions, mixing verified, inferred and target-state claims. | Convert the master document into current state plus ADRs and roadmap. Generate stack/version sections from manifests and require evidence links for verified claims. | Master Documentation V2 and current source bundle. | Stabilization | M | TBD |  | Required
CEO-064 | No formal architecture decision record trail | Open | Governance | Medium | P1 | Major decisions such as source adapters, client-side comparison, global stores, native fullscreen and connector execution are not backed by an ADR trail. | Create concise ADRs for canonical model, job architecture, connector boundary, identity policy, overlay ownership, snapshot storage and AI governance. | No ADR directory or decision records identified in bundle. | Architecture foundation | M | TBD |  | Required
CEO-065 | AI readiness depends on unresolved deterministic foundations | Open | Strategy | High | P0 | AI can amplify comparison and change review, but weak identity, provenance, permissions, snapshot reproducibility and evidence contracts would make answers unsafe or untrustworthy. | Treat canonical snapshots, evidence citations, authorization, typed tool APIs and evaluation fixtures as prerequisites. Keep deterministic results usable when AI is absent. | Current AI direction plus platform gaps in identity, auth and persistence. | CEO decision | L | TBD |  | Required

## Executive Dashboard
CEO Review Issue Dashboard
Baseline | 14 August 2026 | Mode | Selective Expansion | Total issues
Severity | Count | Priority | Count | Status | Count
Critical |  | P0 |  | Open
High |  | P1 |  | In Progress
Medium |  | P2 |  | Blocked
Low |  |  |  | Resolved
Deferred
Recommended sequence
1 | Contain trust and security risks | Auth boundary, secrets, exports, raw diagnostics, demo-data labeling
2 | Stabilize current pilot | Bounded polling, typed errors, state cleanup, regression smoke suite
3 | Build the durable foundation | Canonical model, snapshots, jobs, schema validation, observability
4 | Strengthen deterministic intelligence | Identity governance, match corpus, source-pair calibration, units/context
5 | Productize the hero workflow | Engineering Change and Discrepancy Review, saved workspaces, action reports
6 | Scale and govern | Server-side workers, LOD, access controls, retention, deployment safety

## CEO Decisions
Decision ID | Decision | Recommendation | Status | Rationale | Options | Owner | Target Date
D-01 | Primary product wedge | Engineering Change and Discrepancy Review | Recommended | Combines the strongest existing capabilities into one high-value outcome. | A: Source workspace only ¦ B: Change/discrepancy review ¦ C: Generic digital-thread portal | TBD | TBD
D-02 | Target architecture approach | Progressive strangler modernization | Recommended | Preserves working integrations while replacing fragile boundaries deliberately. | A: Hardening only ¦ B: Progressive strangler ¦ C: Full rewrite | TBD | TBD
D-03 | Production release boundary | Do not call production-ready until P0 gates close | Recommended | Current security, jobs, persistence, testing and observability are insufficient. | A: Demo pilot ¦ B: Controlled internal pilot ¦ C: Production | TBD | TBD
D-04 | Canonical model | Adopt occurrence-aware, provenance-first snapshot model | Recommended | Reliable comparison and AI grounding require context, identity and lineage. | A: Extend attributes ¦ B: Canonical snapshot + compatibility projection | TBD | TBD
D-05 | AI dependency rule | AI follows deterministic foundation | Recommended | Prevents confident but ungrounded recommendations and preserves safe degradation. | A: AI-first UI ¦ B: Evidence-first tools then AI | TBD | TBD